## Summary
retailer-x — Databricks assessment — DRAFT, unreviewed
Generated 2026-10-08 · Velox Databricks accelerator · INTERNAL
Project | retailer-x
Decision (Axis C) | This report is for the Retailer X platform owner (name: ?) to decide which workloads move to Databricks, in which waves, and what must be fixed first (GDPR erasure, EU residency, security posture), including whether the existing workspace deployment is kept, redone or discarded, before the migration is committed (date: ?). assumed — OQ-01, OQ-02
Counts
Requirements | 15
Business rules | 18
Inventory objects | 38
Findings | 50
Readiness (lowest scored of 5) | 1
Open questions (open) | 15
of which blocking (impact high) | 6
Rationalization
migrate | 8
modernize | 10
retire | 8
defer | 4
undecided | 0
Business rules by status
CODE-ONLY | 4
CONFIG-ONLY | 2
CONFLICT | 4
UNRESOLVED | 1
VERIFIED | 7
Evidence gaps (❌/⚠️) | 7
Which workloads to retire — Usage ≥ 90 days incl. month/quarter end
Migration effort — Complexity per workload + trial conversion
Erasure completeness on Databricks — Every PII surface + reach proof
EU residency — Region of every store and processor
Data volume / sizing — Row counts and growth from production
Cost baseline — Current spend + Databricks usage
**Usage window** — Source / start / end

## Readiness
Dimension | Score (1–5) | Counts toward overall | Basis | Rationale | Needs | Evidence | Review status
data |  | — | code | All data is synthetic (≈1.5k rows per table in the workspace); no source, volume or history depth is known. | real source systems and production volumes (OQ-04) | SELECT count(*) FROM eurostream.bronze.orders → 1500 | extracted
logic | 3 | ✓ | code | 18 rules recovered: 7 VERIFIED, 4 CONFLICT, 4 CODE-ONLY, 2 CONFIG-ONLY, 1 UNRESOLVED; the conflicts sit on the erasure/consent critical path. |  | src/eurostream/warehouse.py:484 | extracted
governance | 1 | ✓ | workspace | PII processed in us-east-2 against ADR 0001; public HF copy; erasure misses bus, HF and the rebuild path; no UC tags, masks or grants. |  | system.billing.usage → *_US_EAST_OHIO | extracted
security | 2 | ✓ | workspace | Read as workspace-assessor (the assessment service principal). 31 checks pass, 24 fail (4 high); weighted coverage 75% of the SAT catalog | not assessed — 11 account-level API: needs account admin, or SAT results; 1 needs a run on cluster compute, or SAT results; 1 pass over what this identity can see only; needs a workspace admin read | posture.json | extracted
operations | 2 | ✓ | workspace | Existing jobs run as a person and mostly failed (pipeline 1/5); the deployed code is not in VCS; CI deploys on every push. |  | system.lakeflow.job_run_timeline → eurostream_pipeline runs=5 ok=1 | extracted

## Decisions
ID | Question | Why it matters | Who to ask | Default if unanswered | Impact if wrong | Blocks | Evidence
OQ-01 | Why move to Databricks now, and who decides? The RFC calls EuroStream a portfolio artefact; is this assessment for a production go/no-go, a reference migration, or a demo? | The decision the report serves (Axis C) and the depth of scope depend on it. | Platform owner / sponsor (name: ?) | Treat as a production migration decision for the platform owner | high | SCOPE-01 | docs/rfc/0001-platform-design.md §Problem statement
OQ-02 | The workspace already runs a eurostream catalog, 4 jobs and Lakeflow pipelines from a databricks/ folder removed from the repo on 2026-10-08. Keep and repair it as the starting point, rebuild from scratch, or discard? | It decides whether wave 1 is a repair or a new build. The deployment is in us-east-2 (FND-01), mostly failing (FND-19) and not in VCS (FND-18). | Platform owner (name: ?) with thuyhoang@kms-technology.com (deployer) | Treat as a reference design only; rebuild under a bundle in an EU workspace | high | obj-50, obj-51, obj-52, obj-55 | system.lakeflow.job_run_timeline → eurostream_pipeline runs=5 ok=1
OQ-03 | Is there any legal basis for processing EU customer data in us-east-2, and in which EU region must the target workspace and metastore live? Where are Aiven Kafka and Turso hosted? | ADR 0001 forbids processing outside the EU; the workspace bills to US_EAST_OHIO. | DPO (name: ?) | No basis; target workspace in eu-central-1 | high | SEC-01, FND-01 | docs/adr/0001-eu-region-choice.md:22
OQ-04 | Which real systems produce orders, clicks and payments, in what format, at what rate and volume? Today all events come from a synthetic generator. | Ingestion pattern (Kafka, Lakeflow Connect, files), sizing and cost depend on it. | Platform owner (name: ?) | Kafka topics as today, ≤ 1M events/day | high | obj-30, INT-01 | src/eurostream/producers.py:114
OQ-05 | Must the public Hugging Face dataset swadhinbiswas/eustream continue to exist? It holds pseudonymized customer rows, is public by default, and erasure never reaches it. | It is personal data published outside the EU (FND-04). | DPO (name: ?) and Platform owner | Retire it; offer an anonymized aggregate via Delta Sharing if needed | high | obj-20, obj-36 | .github/workflows/orchestrate.yml:90
OQ-11 | Has any erasure been undone by a full Silver rebuild in production? | The code path exists (FND-02); a regulator-facing question if it happened. | DPO (name: ?) | Unknown; check audit log against silver.customers | high | BR-10 | src/eurostream/warehouse.py:484

## Rationalization
Object ID | Kind | Name | Disposition | Wave | In use | Usage window (days) | Covers month-end | Complexity | Complexity source | On critical path | Riskiest rule | Owner agreed | Target component | Blocks | Evidence | Notes
obj-01 | queue | topic orders | modernize | 1 |  |  |  | M | manual | ✓ | VERIFIED |  | <catalog>.bronze.orders streaming table from Kafka (PII tokenized at producer) | OQ-04, OQ-13 | src/eurostream/producers.py:114 | FND-03
obj-02 | queue | topic payments | modernize | 2 |  |  |  | M | manual | ✓ | VERIFIED |  | <catalog>.bronze.payments streaming table from Kafka | OQ-04 | src/eurostream/producers.py:21
obj-03 | queue | topic clicks | migrate | 1 |  |  |  | L | manual | — | VERIFIED |  | <catalog>.bronze.clicks streaming table | OQ-04 | src/eurostream/producers.py:20 | no Silver reader in code
obj-06 | file_store | events.db (SqliteBus) | retire |  | ✓ |  |  | L | manual | — |  |  | none — local stand-in replaced by Kafka source |  | docs/adr/0002-event-bus.md:23 | local-only by design (ADR 0002); retire = not migrated
obj-07 | table | bronze.orders | migrate | 1 | ✓ |  |  | M | manual | ✓ | VERIFIED |  | <catalog>.bronze.orders (Lakeflow streaming table, PII tagged + masked) | OQ-02 | src/eurostream/warehouse.py:32
obj-08 | table | bronze.payments | migrate | 2 | ✓ |  |  | L | manual | ✓ | VERIFIED |  | <catalog>.bronze.payments |  | src/eurostream/warehouse.py:41
obj-09 | table | bronze.clicks | migrate | 1 | ✓ |  |  | L | manual | — | VERIFIED |  | <catalog>.bronze.clicks |  | src/eurostream/warehouse.py:37
obj-10 | table | bronze.fraud_alerts | migrate | 2 | ✓ |  |  | L | manual | ✓ | VERIFIED |  | <catalog>.bronze.fraud_alerts (idempotent on alert_id) |  | src/eurostream/warehouse.py:46
obj-11 | table | silver.customers | defer | 1 | ✓ |  |  | H | manual | ✓ | CONFLICT |  | <catalog>.silver.customers (AUTO CDC, suppression anti-join, HMAC from secret scope) | OQ-07, OQ-08, OQ-11 | src/eurostream/warehouse.py:484 | CONFLICT rules BR-10/BR-12 and UNRESOLVED BR-06 — cannot migrate as-is; redesign once owners answer
obj-12 | table | silver.orders / silver.payments | modernize | 1 | ✓ |  |  | M | manual | ✓ | VERIFIED |  | <catalog>.silver.orders / payments (AUTO CDC, expectations, quarantine without clear PII) | OQ-10 | src/eurostream/warehouse.py:508 | FND-10, FND-15
obj-13 | table | gold.customer_360 | defer | 1 | ✓ |  |  | M | manual | ✓ | UNRESOLVED |  | <catalog>.gold.customer_360 materialized view + UC metric view for consent KPIs | OQ-07 | src/eurostream/warehouse.py:554 | pilot candidate once the consent rule is settled
obj-14 | table | gold.order_facts / gold.fraud_summary | migrate | 2 | ✓ |  |  | M | manual | — | VERIFIED |  | <catalog>.gold.order_facts / fraud_summary materialized views |  | src/eurostream/warehouse.py:76
obj-15 | table | governance.suppression_registry | migrate | 0 | ✓ |  |  | L | manual | ✓ | CONFLICT |  | <catalog>.governance.suppression_registry (Delta, MERGE) |  | src/eurostream/warehouse.py:97 | must exist before any Silver load
obj-16 | table | governance.erasure_audit_log + JSONL | modernize | 0 | ✓ |  |  | L | manual | — | CODE-ONLY |  | <catalog>.governance.erasure_audit_log with per-surface status, HMAC confirmation |  | src/eurostream/governance/erasure.py:253 | FND-08, FND-25
obj-17 | table | governance.watermarks / data_quality_runs / lineage_events / pii_manifest | retire |  | ✓ |  |  | L | manual | — |  |  | replaced by pipeline checkpoints, expectations event log, UC lineage, UC governed tags |  | src/eurostream/warehouse.py:94 | retire = superseded by a native feature, not unused
obj-19 | export | data/lake Parquet export | retire |  | ✓ |  |  | L | manual | — |  |  | none — Delta tables are the lake | OQ-05 | src/eurostream/warehouse.py:795
obj-20 | object_store | Hugging Face public dataset | retire | 0 |  |  |  | L | manual | — |  |  | Delta Sharing of an anonymized aggregate, if required | OQ-05 | .github/workflows/orchestrate.yml:90 | FND-04 — stop the upload before migration
obj-21 | table | Turso remote mirror | retire | 3 |  |  |  | M | manual | — |  |  | Lakebase synced table or SQL warehouse for app reads | OQ-15 | src/eurostream/governance/erasure.py:230
obj-22 | file_store | GitHub Actions cache | retire | 0 | ✓ |  |  | L | manual | — |  |  | none |  | .github/workflows/orchestrate.yml:22
obj-30 | job | Synthetic event producers | defer |  | ✓ |  |  | L | manual | — |  |  | real source connectors (TBD) | OQ-04 | src/eurostream/producers.py:114 | keep only as a test-data generator
obj-31 | job | Fraud stream processor | modernize | 2 | ✓ |  |  | H | manual | ✓ | CONFIG-ONLY |  | Structured Streaming job (transformWithState, checkpoint) on serverless | OQ-09, OQ-12 | src/eurostream/streaming.py:54 | FND-12
obj-32 | job | Medallion DAG | modernize | 1 | ✓ |  |  | H | manual | ✓ | CONFLICT |  | Lakeflow Declarative Pipeline (bronze→silver→gold) + Lakeflow Job, deployed by bundle | OQ-02 | .github/workflows/orchestrate.yml:4 | FND-15, FND-26
obj-33 | job | Quality gates + PII gate | modernize | 1 | ✓ |  |  | M | manual | ✓ | CONFLICT |  | Lakeflow expectations + UC data classification |  | src/eurostream/quality.py:103 | FND-11, FND-14
obj-34 | job | Erasure service | modernize | 0 | ✓ |  |  | H | manual | ✓ | CONFLICT |  | Lakeflow Job: registry MERGE → bronze mask → pipeline refresh → REORG PURGE/VACUUM → audit; run_as service principal | OQ-06 | src/eurostream/governance/erasure.py:108 | FND-02, FND-03, FND-20
obj-35 | job | Turso sync | retire | 3 |  |  |  | M | manual | — |  |  | none | OQ-15 | .github/workflows/orchestrate.yml:77
obj-36 | job | Hugging Face lake upload | retire | 0 | ✓ |  |  | L | manual | — |  |  | none | OQ-05 | .github/workflows/orchestrate.yml:85
obj-37 | api_endpoint | FastAPI service | modernize | 3 |  |  |  | M | manual | — | CODE-ONLY |  | Databricks App (OAuth, on-behalf-of SQL) + erasure job trigger | OQ-14 | src/eurostream/api.py:206 | FND-05, FND-06
obj-38 | ui_view | HTML dashboard | modernize | 3 |  |  |  | L | manual | — | CODE-ONLY |  | AI/BI dashboard or the Databricks App UI | OQ-14 | src/eurostream/api.py:62
obj-39 | job | Schema contract check | migrate | 1 | ✓ |  |  | L | manual | — |  |  | CI step + Delta schema enforcement |  | src/eurostream/contracts.py:134
obj-55 | job | Existing Databricks jobs and pipelines (us-east-2) | defer |  | — | 8 |  |  |  | — |  |  | reference design for the EU rebuild | OQ-02, OQ-03 | system.lakeflow.job_run_timeline → no runs after 2026-09-28 | FND-18, FND-19

## Findings
ID | Severity | Category | Layer | Title | Impact | Detail | When migrated | Evidence kind | Requirements raised | Questions raised | Evidence | Review status
FND-09 | high | logic | transform | Consent: one historical opt-out blocks a later opt-in forever | Under-counts consenting customers; a business rule nobody has confirmed. | silver.customers.marketing_consent = bool_and(marketing_consent) over every order ever placed, while email/iban use the latest value (arg_max). | carried | stated | DR-01 | OQ-07 | src/eurostream/warehouse.py:496 | extracted
FND-08 | medium | governance | ops | Erasure audit says 'completed' when a remote copy failed | Overstated proof of erasure to a data subject or regulator. | Turso erasure errors are caught and logged as warnings. 'lake' is added to layers_touched before the refresh callback runs. Status is always 'completed'. | carried | stated | SEC-04 |  | src/eurostream/governance/erasure.py:130 | extracted
FND-01 | critical | governance | store | EU customer PII is stored and processed in a US-region workspace | A GDPR Chapter V transfer issue today, unless a transfer basis exists; the whole existing deployment would need to move. | All workspace compute and storage bill to US_EAST_OHIO SKUs; eurostream.bronze.orders holds clear email/iban. ADR 0001 requires EU-only storage and processing, and no transfer outside the EU. | redesign | stated | SEC-01 | OQ-03 | SELECT … FROM system.billing.usage → PREMIUM_JOBS_SERVERLESS_COMPUTE_US_EAST_OHIO; docs/adr/0001-eu-region-choice.md:22 | extracted
FND-02 | high | governance | transform | Erased customers reappear in Silver/Gold on the next full rebuild | An erasure is undone by the next full transform; a faithful migration carries it into Lakeflow. | build_silver deletes and re-inserts silver.customers from bronze.orders grouped by customer_id with no suppression_registry filter. Erasure only masks Bronze, so the customer_id comes back. | redesign | stated | SEC-02 | OQ-11 | src/eurostream/warehouse.py:484 | extracted
FND-03 | high | governance | ingest | Erasure never reaches the event bus; topics carry clear PII | Replaying a topic restores erased PII into Bronze; on Databricks a Kafka source with startingOffsets=earliest would do the same. | Order events carry email and iban in clear text; payments carry iban, clicks ip_address. Erasure updates warehouse tables only; nothing deletes or compacts Kafka topics or the SQLite messages log. | redesign | stated | SEC-02 | OQ-13 | src/eurostream/producers.py:114; src/eurostream/governance/erasure.py:171 | extracted
FND-04 | high | governance | serving | Pseudonymized customer data is published to a public Hugging Face dataset | Pseudonymous data is still personal data under GDPR; a public copy outside the EU cannot be recalled. | orchestrate.yml creates the dataset without private=True and uploads data/lake (customer_id, email_hash, iban_hash) every 4 h. Erasure never reaches it. The provider region is unknown. | redesign | stated | SEC-01, SEC-02 | OQ-05 | .github/workflows/orchestrate.yml:90 | extracted
FND-05 | high | security | serving | API has no authentication; erase and customer endpoints are public | Anyone can trigger erasures or read the customer table. | No auth dependency on any route, including POST /erase/{customer_id}, POST /transform and GET /gold/customer-360. CORS allows any origin with credentials. The service is deployed on Render with autoDeploy. | redesign | stated |  | OQ-14 | src/eurostream/api.py:52; src/eurostream/api.py:206 | extracted
FND-06 | high | security | serving | SQL injection in GET /verify-erasure/{customer_id} | Arbitrary SQL against the warehouse from an unauthenticated endpoint. | Five queries interpolate the raw path parameter with f-strings; the S608 lint is suppressed with noqa. /gold/customer-360 search is only quote-doubled. | redesign | stated |  |  | src/eurostream/api.py:239 | extracted
FND-07 | high | security | transform | PII salt has a public hard-coded default and is inlined into SQL | Anyone with the repo can reverse low-entropy hashed emails and IBANs, so the hashes give no pseudonymization. | PII_SALT = "eurostream-pii-salt" in config.py; docker-compose does not override it; build_silver interpolates it into SQL text. | redesign | stated | DR-02 | OQ-08 | src/eurostream/config.py:22; src/eurostream/warehouse.py:492 | extracted
FND-10 | high | data_quality | transform | Late events are lost by the event-time watermark | Events arriving late or with an equal timestamp are never processed. | Incremental Silver reads WHERE occurred_at > watermark (= max bronze.orders.occurred_at). Payments reuse the orders watermark; ingested_at is stored but unused. | resolved-by-target | stated |  | OQ-10 | src/eurostream/warehouse.py:636 | extracted
FND-12 | high | logic | ingest | Fraud scorer state is lost on restart while offsets advance | Missed VELOCITY / AMOUNT_ZSCORE alerts and lost alerts after any restart. | Offsets are committed per record. FraudScorer.checkpoint/restore exist but are never called. Alerts are produced asynchronously with no flush before commit. | resolved-by-target | stated | FR-01 |  | src/eurostream/streaming.py:162 | extracted
FND-17 | high | governance | store | Workspace has no PII tags, masks, row filters or grants on the eurostream catalog | No least-privilege model is in place; quarantine tables leak clear PII past the Silver boundary. | Zero column tags, column masks or row filters. The only grant is BROWSE to the assessor principal. Clear email/iban sit in bronze.orders, orders_files and silver.*_quarantine, so access rests entirely on ownership by one user. | redesign | stated | DR-03 |  | SELECT count(*) FROM system.information_schema.column_masks WHERE table_catalog='eurostream' → 0; information_schema.columns → silver.orders_quarantine.email:STRING, iban:STRING | extracted
FND-18 | high | scope | ops | Live workspace deployment has no source in the repository | The prior attempt cannot be rebuilt, reviewed or promoted. CI and tests break. | The eurostream catalog, 4 jobs and 3 pipelines were deployed 2026-09-28 from databricks/ (commit 85b9686, 94 files). That folder was removed in c78138d on 2026-10-08. tests/databricks/* and the ci.yml databricks-app job still reference it. | redesign | stated |  | OQ-02 | tests/databricks/test_bundle_contracts.py:6; .github/workflows/ci.yml:36 | extracted
FND-SEC-GOV-21 | high | security | ops | Delegation of the Unity Catalog metastore admin to a group — not met | Deviates from Databricks best practice: Delegate metastore admin to a group who is not the account admin | GOV-21 (Governance): owner=86631d5d-6a48-49da-8777-cd9808dcc04e, created_by=86631d5d-6a48-49da-8777-cd9808dcc04e | redesign | stated |  |  | GET /api/2.1/unity-catalog/metastore_summary; GOV-21 | extracted
FND-SEC-GOV-34 | high | security | ops | Monitor audit logs with system tables (or see GOV-3) — not met | Deviates from Databricks best practice: Configure system tables and set up automated monitoring and alerting | GOV-34 (Governance): {"enable_serverless_compute": "access schema not enabled (state not ENABLE_COMPLETED or MANAGED)"} | redesign | stated |  |  | security_analysis.security_checks run_id=1 check_id=GOV-34; GOV-34 | extracted
FND-SEC-NS-11 | high | security | ops | Workspace IP access list enforcement enabled — not met | Deviates from Databricks best practice: Enable IP access list enforcement so that the configured workspace IP access lists are actually applied — having entries without enforcement leaves the workspace open to access from any IP | NS-11 (Network Security): {"defn": "When enabled, configured IP access lists are enforced for the workspace \u2014 users can only connect from allowed IP addresses"} | redesign | stated |  |  | security_analysis.security_checks run_id=1 check_id=NS-11; NS-11 | extracted
FND-SEC-VX-RES-1 | high | security | ops | Metastore region satisfies the residency requirement — not met | Deviates from Databricks best practice: Place the metastore and workspace in a region the residency requirement allows | VX-RES-1 (Data Protection): metastore region=us-east-2; allowed /^eu-¦europe/ | redesign | stated |  |  | GET /api/2.1/unity-catalog/metastore_summary; VX-RES-1 | extracted
FND-11 | medium | data_quality | transform | Consent quality check cannot fail | False assurance in the quality report. | The check compares two Gold columns populated from the same source column. It never tests consent against the suppression registry or Bronze. | redesign | stated | DR-05 |  | src/eurostream/quality.py:109 | extracted
FND-13 | medium | data_quality | ingest | Malformed events dropped silently | Silent data loss that cannot be measured. | The Bronze loader skips JSON/pydantic failures with bare except/continue. The stream processor counts and commits invalid payloads. There is no dead-letter store. | resolved-by-target | stated |  |  | src/eurostream/warehouse.py:403 | extracted
FND-14 | medium | logic | transform | Quality gate runs after Gold is already overwritten | Bad data is served by the API before the gate fails. | The DAG builds Gold, then runs the gate. A failure blocks only the lake export; Silver/Gold are not rolled back. | redesign | stated | DR-05 |  | src/eurostream/cli.py:251 | extracted
FND-15 | medium | dependency | transform | DuckDB-specific SQL throughout the warehouse layer | Not a transpile; each becomes MERGE or a declarative pipeline (conversion driver). | INSERT OR IGNORE / INSERT OR REPLACE (≥ 11 sites), arg_max, bool_and, COPY … TO PARQUET and read_parquet('hf://…') rely on DuckDB semantics and PK enforcement Delta lacks. | redesign | stated |  |  | src/eurostream/warehouse.py:242 | extracted
FND-16 | medium | concurrency | store | Shared single connections across threads and processes | Lock errors and inconsistent reads under load; import-time side effects in tests. | SqliteBus shares one connection (check_same_thread=False) guarded by a process-local lock while produce and stream run as separate processes. The API shares one DuckDB Warehouse across requests and opens stores at import time. | resolved-by-target | stated |  |  | src/eurostream/bus/sqlite.py:55 | extracted
FND-19 | medium | ops | ops | Existing Databricks jobs mostly failed and have not run since 2026-09-28 | The prior attempt is not a working baseline; reconciliation against it is not possible yet. | eurostream_pipeline 1 of 5 runs succeeded; eurostream_bootstrap 1 of 4; export_lake 7 of 10; art17_erasure 7 of 8. All are unpaused, with no runs after 2026-09-28. | redesign | stated |  | OQ-02 | system.lakeflow.job_run_timeline GROUP BY job → eurostream_pipeline runs=5 ok=1 | extracted
FND-20 | medium | governance | store | Delta retention set to 0 hours on bronze.fraud_alerts | No documented retention policy decides between erasure and recoverability. | delta.deletedFileRetentionDuration = interval 0 hours, with deletion vectors on. This suggests physical purge for erasure, but it removes time travel and can break concurrent readers and streaming. | redesign | stated | SEC-02 | OQ-06 | SHOW TBLPROPERTIES eurostream.bronze.fraud_alerts → delta.deletedFileRetentionDuration=interval 0 hours | extracted
FND-21 | medium | governance | ops | Warehouse with PII cached in GitHub Actions outside the EU-pinned IaC | A PII copy in a non-EU, unmanaged store that erasure does not reach. | orchestrate.yml caches data/eurocart.duckdb and data/events.db. The cache key covers only pii_manifest.json, so state is probably not re-saved between runs. | resolved-by-target | stated | SEC-01 |  | .github/workflows/orchestrate.yml:22 | extracted
FND-22 | medium | security | ops | CI runs with long-lived secrets on every push, no approval gate | Any merged change can publish data or exfiltrate secrets. | The orchestrate and deploy-space workflows run on each push to master with KAFKA_*, TURSO_* and HF_TOKEN. There is no environment: protection or permissions: block. | redesign | stated |  |  | .github/workflows/orchestrate.yml:6 | extracted
FND-23 | medium | documentation | ops | IaC does not describe what runs; residency proof covers AWS only | The 'residency proof' in ADR 0001 does not hold for the real estate. | main.tf declares MSK and S3 in eu-central-1, but the runtime uses Aiven Kafka, Turso, Render, Hugging Face and GitHub Actions. MSK is not deployable as written (subnet_ids defaults to []). | redesign | stated | SEC-01 | OQ-03 | infra/main.tf:3 | extracted
FND-24 | medium | scope | ingest | Sources are synthetic; no real volume or source system is known | Ingestion design, sizing and cost cannot be concluded until real sources are named. | All events come from a Faker-based generator. The RFC calls the system a portfolio artefact. The workspace holds about 1,500 rows per table. | redesign | stated | SCOPE-01 | OQ-04 | docs/rfc/0001-platform-design.md §Problem statement; SELECT count(*) FROM eurostream.bronze.orders → 1500 | extracted
FND-25 | medium | governance | store | Turso mirror and erasure audit hold clear identifiers | Two more PII surfaces to migrate, retire or erase. | Turso mirrors Bronze with clear email/iban/ip_address. The audit log stores clear customer_id with an unsalted, guessable confirmation hash sha256(request_id:customer_id)[:16]. | redesign | stated | SEC-04 | OQ-15 | src/eurostream/governance/erasure.py:241 | extracted
FND-SEC-DP-5 | medium | security | ops | Downloading results is disabled — not met | Deviates from Databricks best practice: Disable download button for notebook results | DP-5 (Data Protection): {"defn": "Enable or disable the download button for notebook results."} | redesign | stated |  |  | security_analysis.security_checks run_id=1 check_id=DP-5; DP-5 | extracted
FND-SEC-NS-5 | medium | security | ops | IP access lists for workspace access — not met | Deviates from Databricks best practice: Configure IP access lists or private network connectivity (NS-3) for workspaces that restrict the IP addresses that can authenticate to help protect against data exfiltration and account takeover | NS-5 (Network Security): {"workspaceId": "7474650345400041"} | redesign | stated |  |  | security_analysis.security_checks run_id=1 check_id=NS-5; NS-5 | extracted
FND-SEC-DP-8 | medium | security | ops | Enable storing interactive notebook results only in the customer account — not met | Deviates from Databricks best practice: Enable store interactive notebook results in your account | DP-8 (Data Protection): {"defn": "When enabled, all interactive notebook results are stored in the customer account."} | redesign | stated |  |  | security_analysis.security_checks run_id=1 check_id=DP-8; DP-8 | extracted
FND-SEC-GOV-15 | medium | security | ops | Enable verbose audit logs (on Azure, diagnostic logs) — not met | Deviates from Databricks best practice: Enable verbose audit logs (on Azure, diagnostic logs) | GOV-15 (Governance): {"defn": "Enable or disable verbose audit logs"} | redesign | stated |  |  | security_analysis.security_checks run_id=1 check_id=GOV-15; GOV-15 | extracted
FND-SEC-DP-9 | medium | security | ops | FileStore endpoint for HTTPS file serving — not met | Deviates from Databricks best practice: Review and disable FileStore endpoint in admin console workspace settings | DP-9 (Data Protection): {"defn": "Enable or disable FileStore endpoint /files"} | redesign | stated |  |  | security_analysis.security_checks run_id=1 check_id=DP-9; DP-9 | extracted
FND-SEC-GOV-28 | medium | security | ops | Govern model assets — not met | Deviates from Databricks best practice: Manage model lifecycle in Unity Catalog | GOV-28 (Governance): | redesign | stated |  |  | security_analysis.security_checks run_id=1 check_id=GOV-28; GOV-28 | extracted
FND-SEC-INFO-29 | medium | security | ops | Streamline the usage and management of various large language model(LLM) providers — not met | Deviates from Databricks best practice: Secure third-party models hosted outside of Databricks with Model Serving to streamline the usage and management of various large language model (LLM) providers such as OpenAI and Anthropic within an organization by storing API keys in one secure location | INFO-29 (Informational): {"message": "No model serving endpoints with endpoint type EXTERNAL_MODEL found"} | redesign | stated |  |  | security_analysis.security_checks run_id=1 check_id=INFO-29; INFO-29 | extracted
FND-SEC-GOV-35 | medium | security | ops | Restrict workspace admins — not met | Deviates from Databricks best practice: Restrict workspace admins to only change a job owner to themselves and the job run as setting to a service principal that they have the Service Principal User role on | GOV-35 (Governance): {"restrict_workspace_admin_settings": "Found status as ALLOW_ALL, to disable the RestrictWorkspaceAdmins set the status to ALLOW_ALL"} | redesign | stated |  |  | security_analysis.security_checks run_id=1 check_id=GOV-35; GOV-35 | extracted
FND-SEC-GOV-36 | medium | security | ops | Automatic cluster update — not met | Deviates from Databricks best practice: Ensure that all the clusters in a workspace are periodically updated to the latest host OS image and security updates | GOV-36 (Governance): {"automatic_cluster_update": "Found status as false to automatic cluster update setting"} | redesign | stated |  |  | security_analysis.security_checks run_id=1 check_id=GOV-36; GOV-36 | extracted
FND-SEC-INFO-42 | medium | security | ops | Git repository allowlist configured — not met | Deviates from Databricks best practice: Enable the Git repository allowlist to restrict which external Git repositories workspace users can connect notebooks to. Without an allowlist users can connect to any external repository enabling code exfiltration and introduction of malicious code from unrev | INFO-42 (Informational): {"defn": "Enable or disable restricting commit and push operations in Repos to a configurable allow list. The allow list will be empty by default."} | redesign | stated |  |  | security_analysis.security_checks run_id=1 check_id=INFO-42; INFO-42 | extracted
FND-SEC-DP-11 | medium | security | ops | SQL warehouse results download disabled — not met | Deviates from Databricks best practice: Disable SQL results download to prevent data exfiltration via SQL Editor and Dashboards | DP-11 (Data Protection): sql_results_download=True | redesign | stated |  |  | GET /api/2.0/settings/types/sql_results_download/names/default; DP-11 | extracted
FND-SEC-DP-13 | medium | security | ops | DBFS file browser disabled — not met | Deviates from Databricks best practice: Disable the DBFS file browser to prevent users from browsing shared storage paths through the UI without an audit trail or access control | DP-13 (Data Protection): {"defn": "Enable or disable DBFS File Browser"} | redesign | stated |  |  | security_analysis.security_checks run_id=1 check_id=DP-13; DP-13 | extracted
FND-SEC-GOV-42 | medium | security | ops | Jobs run as service principal — not met | Deviates from Databricks best practice: Configure production jobs to run as a service principal to enforce least privilege and improve audit clarity | GOV-42 (Governance): 7 jobs; run as a person: ['SAT Driver Notebook', 'SAT Initializer Notebook (one-time)', 'SAT Secrets Scanner', 'eurostream_pipeline', 'eurostream_art17_erasure'] | redesign | stated |  |  | GET /api/2.2/jobs/list; GOV-42 | extracted
FND-SEC-VX-IA-1 | medium | security | ops | Maximum lifetime of new tokens is 90 days or less — not met | Deviates from Databricks best practice: Set maxTokenLifetimeDays to 90 or less; SAT IA-5 only checks that a limit exists | VX-IA-1 (Identity & Access): maxTokenLifetimeDays=730 | redesign | stated |  |  | GET /api/2.0/preview/workspace-conf?keys=maxTokenLifetimeDays → maxTokenLifetimeDays=730; VX-IA-1 | extracted
FND-26 | low | ops | ops | Hand-maintained lineage and custom DAG runner | Lineage is wrong today; there is no scheduler. | Lineage lists are typed by hand per task and omit bronze.fraud_alerts and gold.fraud_summary. The DAG is an in-process sequential runner with max_retries=1. | resolved-by-target | stated |  |  | src/eurostream/cli.py:237 | extracted
FND-SEC-DP-6 | low | security | ops | Notebook export — not met | Deviates from Databricks best practice: Disable exporting notebooks and cells within notebooks | DP-6 (Data Protection): {"defn": "Enable or disable exporting notebooks and cells within notebooks."} | redesign | stated |  |  | security_analysis.security_checks run_id=1 check_id=DP-6; DP-6 | extracted
FND-SEC-DP-7 | low | security | ops | Notebook table clipboard features — not met | Deviates from Databricks best practice: Disable the ability of users to copy tabular data to the clipboard via the notebooks UI | DP-7 (Data Protection): {"defn": "Enable or disable the ability of users to copy tabular data to the clipboard via the Notebooks UI."} | redesign | stated |  |  | security_analysis.security_checks run_id=1 check_id=DP-7; DP-7 | extracted
FND-SEC-DP-14 | low | security | ops | Store and retrieve embeddings securely — not met | Deviates from Databricks best practice: Store and retrieve embeddings securely using the Vector Search | DP-14 (Data Protection): {"vector_search_endpoint_list": "No Vector Search Endpoints found"} | redesign | stated |  |  | security_analysis.security_checks run_id=1 check_id=DP-14; DP-14 | extracted
FND-SEC-INFO-38 | low | security | ops | Third-party library control — not met | Deviates from Databricks best practice: Add libraries and init scripts to the allowlist in Unity Catalog | INFO-38 (Informational): {"third_party_library_control": "No artifact allowlist configured"} | redesign | stated |  |  | security_analysis.security_checks run_id=1 check_id=INFO-38; INFO-38 | extracted
FND-SEC-INFO-39 | low | security | ops | Compliance security profile for the workspace — not met | Deviates from Databricks best practice: Validate and deploy on a platform that has put in place controls to meet the unique compliance needs of highly regulated industries | INFO-39 (Informational): {"compliance security profile setting for this workspace": "False"} | redesign | stated |  |  | security_analysis.security_checks run_id=1 check_id=INFO-39; INFO-39 | extracted
FND-SEC-INFO-40 | low | security | ops | Enhanced security monitoring for the workspace — not met | Deviates from Databricks best practice: Validate and deploy on a platform that has put in place controls to meet the unique compliance needs of highly regulated industries | INFO-40 (Informational): {"enhanced security monitoring for this workspace": "False"} | redesign | stated |  |  | security_analysis.security_checks run_id=1 check_id=INFO-40; INFO-40 | extracted

## Business Rules
ID | Name | Rule status | Logic | In plain words | Anchor (object · hash) | Config-driven | In the spec | Requirements | Open questions | Locator | Review status
BR-01 | Velocity fraud rule | VERIFIED | count of payments per customer in window > fraud_velocity_threshold (5) within fraud_window_seconds (300); alert at count == threshold+1 | Flag a customer who makes more than 5 payments in 5 minutes; alert once per window | FraudScorer.score | ✓ | ✓ | FR-01 |  | src/eurostream/streaming.py:100; README.md §Streaming fraud engine | extracted
BR-02 | Amount z-score fraud rule | VERIFIED | abs(amount_eur - mean)/std > fraud_amount_zscore (3.0) over last 200 payments per customer | Flag a payment more than 3 standard deviations from the customer's usual amount | FraudScorer.score | ✓ | ✓ | FR-01 |  | src/eurostream/streaming.py:116 | extracted
BR-03 | Geo mismatch fraud rule | VERIFIED | billing country != merchant country | Flag a payment whose billing country differs from the merchant's country | FraudScorer.score | — | ✓ | FR-01 |  | src/eurostream/streaming.py:138 | extracted
BR-04 | Fraud thresholds live in configuration | CONFIG-ONLY | fraud_velocity_threshold=5, fraud_window_seconds=300, fraud_amount_zscore=3.0; x or settings.x means an explicit 0 falls back | Fraud sensitivity is set by environment variables, not code; nobody named owns them | Settings.fraud_* | ✓ | — | FR-01 | OQ-09 | src/eurostream/config.py:87 | extracted
BR-05 | Silver pseudonymization | VERIFIED | sha256('{salt}:' ¦¦ arg_max(email, occurred_at)); same for iban | Email and IBAN are replaced by a salted hash of the latest value; same input gives same hash | Warehouse.build_silver | ✓ | ✓ | DR-02 | OQ-08 | src/eurostream/warehouse.py:492; README.md §Append-only event history | extracted
BR-06 | Consent = AND over all orders | UNRESOLVED | bool_and(marketing_consent) GROUP BY customer_id over all bronze.orders | A customer counts as consenting only if every order ever placed carried consent; a later opt-in never overrides an old opt-out | Warehouse.build_silver | — | ✓ | DR-01 | OQ-07 | src/eurostream/warehouse.py:496; README.md §Medallion storage | extracted
BR-07 | Order/payment dedup tie-break | CODE-ONLY | row_number() OVER (PARTITION BY order_id ORDER BY occurred_at) = 1 | When an order arrives twice, keep the earliest version | Warehouse.build_silver | — | — |  |  | src/eurostream/warehouse.py:508 | extracted
BR-08 | Incremental watermark on event time | VERIFIED | WHERE occurred_at > watermark; watermark = max(bronze.orders.occurred_at), reused for payments | Each run only processes events newer than the newest order seen; late events are skipped | Warehouse.build_silver_incremental | — | ✓ |  | OQ-10 | src/eurostream/warehouse.py:636; README.md §Medallion storage | extracted
BR-09 | Erasure masks Bronze, deletes Silver/Gold/fraud alerts | VERIFIED | UPDATE bronze.* SET email/iban/ip_address='<anonymized>'; DELETE silver.*, gold.*, bronze.fraud_alerts WHERE customer_id=? | On erasure the raw rows stay with PII overwritten; derived rows are deleted | ErasureService._anonymize_warehouse | — | ✓ | SEC-02 |  | src/eurostream/governance/erasure.py:206; docs/gdpr_erasure_flow.md §The cascade | extracted
BR-10 | Suppression honoured at Silver rebuild | CONFLICT | build_silver: DELETE FROM silver.customers; INSERT … FROM bronze.orders GROUP BY customer_id — no suppression_registry filter | Docs say an erased customer stays suppressed; the full rebuild re-creates them from masked Bronze rows | Warehouse.build_silver | — | ✓ | SEC-02 | OQ-11 | src/eurostream/warehouse.py:484 | extracted
BR-11 | Quality gate blocks publication | CONFLICT | quality_gate runs after build_gold; failure only blocks export_lake | Docs say a failed check aborts the DAG; in code Silver/Gold are already overwritten when the gate runs | cli.transform DAG | — | ✓ | DR-05 |  | src/eurostream/cli.py:251 | extracted
BR-12 | Consent quality check | CONFLICT | count(*) FROM gold.customer_360 WHERE consents_marketing <> marketing_consent, both from the same column | The consent check can never fail; it does not test the suppression registry or upstream consent | QualityGate._check_consent_gated | — | ✓ | DR-01 |  | src/eurostream/quality.py:109 | extracted
BR-13 | PII column classification | VERIFIED | majority vote ≥ 0.6 over sampled values; IBAN mod-97 for 11 country codes; gate samples 200 bronze.orders rows only | New columns are flagged as PII when 60% of a sample looks like PII; only the orders feed is scanned | pii.classify_column | — | ✓ | DR-06 |  | src/eurostream/governance/pii.py:84; docs/adr/0003-pii-classification.md:45 | extracted
BR-14 | /stats falls back to the public HF lake | CODE-ONLY | if local total == 0: read hf://datasets/swadhinbiswas/eustream/*.parquet; silver/orders count mapped to key silver_customers | When the local warehouse is empty the dashboard shows numbers from the public dataset, one of them mislabelled | api.stats | — | — |  |  | src/eurostream/api.py:141 | extracted
BR-15 | /fraud_alerts falls back to gold summary | CODE-ONLY | except Exception: SELECT * FROM gold.fraud_summary | If raw alerts cannot be read, the endpoint silently returns the aggregate instead | api.fraud_alerts | — | — |  |  | src/eurostream/api.py:508 | extracted
BR-16 | Erasure audit status always 'completed' | CODE-ONLY | status='completed' set unconditionally; Turso errors logged as warning; 'lake' added to layers_touched before the callback runs | The audit can say an erasure is complete when a remote copy or the lake refresh failed | ErasureService.execute | — | — | SEC-04 |  | src/eurostream/governance/erasure.py:130 | extracted
BR-17 | Streaming suppression check | CONFLICT | suppression_check=erasure.is_suppressed passed to the processor; set seeded once at construction | A running fraud processor only learns of new erasures made in its own process | ErasureService.is_suppressed | — | ✓ | SEC-02 |  | src/eurostream/governance/erasure.py:80 | extracted
BR-18 | Default consent | CONFIG-ONLY | consent_default: bool = False | An event that carries no consent flag is treated as not consenting | Settings.consent_default | ✓ | — | DR-01 | OQ-07 | src/eurostream/config.py:81 | extracted

## Requirements
ID | Type | Priority | Title | Statement | Domain | Inferred | Confidence | Conflicts | Open questions | Target layer | Target object | Owner | Evidence | Review status
FR-01 | functional |  | Rule-based payment fraud scoring | Score each payment against VELOCITY (>5 in 300 s), AMOUNT_ZSCORE (>3.0σ, last 200) and GEO_MISMATCH and emit alerts to bronze.fraud_alerts. | fraud | — | 0.9 |  |  | bronze | <catalog>.bronze.fraud_alerts |  | README.md §Streaming fraud engine | extracted
NFR-01 | nonfunctional |  | Fraud alert latency | Fraud alerts surface within one fraud window (300 s); RFC goal says sub-minute. | fraud | — | 0.7 | src-docs@docs/rfc/0001-platform-design.md §Goals: 'sub-minute (here: near-instant) latency' | OQ-12 | bronze |  |  | docs/architecture.md §SLOs | extracted
SEC-01 | security |  | EU data residency for all storage and processing | All storage and processing pinned to EU regions; no code path transfers data outside the EU; DR must stay EU-only. | governance | — | 0.95 | src-ws@system.billing.usage → sku PREMIUM_*_US_EAST_OHIO: workspace and metastore in us-east-2 | OQ-03 | platform |  |  | docs/adr/0001-eu-region-choice.md:22 | extracted
SEC-02 | security |  | Right to erasure cascade (Art. 17) | An erasure request adds the customer to the suppression registry, masks Bronze PII, deletes Silver/Gold/fraud-alert rows and re-snapshots the lake. | governance | — | 0.9 |  | OQ-06 | platform |  |  | docs/gdpr_erasure_flow.md §The cascade | extracted
SEC-03 | security |  | Erasure SLA 60 seconds (application target) | The cascade completes within EUROSTREAM_ERASURE_SLA_SECONDS (60); a breach counter increments otherwise. Not the statutory period. | governance | — | 0.95 |  | OQ-06 | platform |  |  | docs/gdpr_erasure_flow.md §SLA | extracted
SEC-04 | security |  | Auditable erasure trail | Each erasure writes an audit record (JSONL + governance.erasure_audit_log) with a confirmation hash. | governance | — | 0.9 |  |  | gold | <catalog>.governance.erasure_audit_log |  | docs/gdpr_erasure_flow.md §Audit trail | extracted
DR-01 | data |  | Marketing consent propagates to Gold | marketing_consent is carried to Gold; non-consenting customers must not flow into marketing-facing aggregates. The serving filter is outside the repo. | marketing | — | 0.85 | src-docs@README.md §Medallion storage: 'this repository does not include a downstream marketing-serving filter' | OQ-07 | gold | <catalog>.gold.customer_360 |  | docs/rfc/0001-platform-design.md §Goals | extracted
DR-02 | data |  | Pseudonymize PII at the Silver boundary | Silver stores salted SHA-256 of email and IBAN; the salt must be secret in production. | governance | — | 0.9 |  | OQ-08 | silver |  |  | README.md §Append-only event history | extracted
DR-03 | data |  | Clear PII only in internal Bronze; Bronze never exported | Bronze keeps clear-text email, IBAN and IP by design for internal use; public exports exclude Bronze. | governance | — | 0.9 |  |  | bronze |  |  | docs/architecture.md §Bronze | extracted
DR-04 | data |  | Event schema contracts enforced in CI | Event model schemas are snapshotted to governance/contracts.json; CI fails on breaking drift. | platform | — | 0.9 |  |  | bronze |  |  | docs/rfc/0001-platform-design.md §Key design decisions | extracted
DR-05 | data |  | Quality gates abort the DAG | Six checks (uniqueness ×2, PII-not-clear ×2, consent gating, referential integrity) run after transform; any failure aborts the DAG. | platform | — | 0.85 | src-docs@docs/rfc/0001-platform-design.md: RFC says 'five checks' |  | silver |  |  | README.md §Data quality and IBAN validation | extracted
DR-06 | data |  | Fail on unregistered PII columns | A new PII-looking column not in governance/pii_manifest.json fails the pipeline (60% majority vote, IBAN mod-97). | governance | — | 0.9 |  |  | bronze |  |  | docs/adr/0003-pii-classification.md:50 | extracted
INT-01 | integration |  | Event bus Kafka (Aiven) / SQLite local | Topics orders, clicks, payments, fraud_alerts, erasure_requests; backend chosen by EUROSTREAM_EVENT_BUS_BACKEND; MSK on AWS as deployment target. | platform | — | 0.85 |  | OQ-04 | bronze |  |  | docs/adr/0002-event-bus.md:23 | extracted
INT-02 | integration |  | Public Parquet lake on Hugging Face | Silver/Gold Parquet is uploaded to a public Hugging Face dataset on a schedule; erasure re-exports the local lake only. | serving | — | 0.85 | src-docs@docs/adr/0001-eu-region-choice.md:52: 'No code path transfers data outside the EU' | OQ-05 | gold |  |  | README.md §Deployment | extracted
SCOPE-01 | scope |  | Portfolio artefact, not production | The RFC states the platform is a portfolio artefact runnable on a laptop with no cloud spend; BI tooling, Kubernetes and ML fraud are non-goals. | platform | — | 0.9 |  | OQ-01 | platform |  |  | docs/rfc/0001-platform-design.md §Problem statement | extracted

## Inventory
ID | Kind | Name | Owner | Layer (best guess) | Rows (est.) | Size (GB) | Schedule | Avg runtime (min) | Runs as | Read by | Written by | Reads | Writes | Consumers | Runs (90 days) | Last read | Last write | Last run | Orphan | PII candidates | Holds PII | Erasure reaches it | Complexity | Complexity source | Disposition | Evidence | Review status
obj-01 | queue | topic orders |  | ingest | [5 empty] | obj-32 | obj-30 | [8 empty] | email, iban | ✓ | — | M | manual |  | src/eurostream/producers.py:114 | extracted
obj-02 | queue | topic payments |  | ingest | [5 empty] | obj-31, obj-32 | obj-30 | [8 empty] | iban | ✓ | — | M | manual |  | src/eurostream/producers.py:21 | extracted
obj-03 | queue | topic clicks |  | ingest | [5 empty] | obj-32 | obj-30 | [8 empty] | ip_address | ✓ | — | L | manual |  | src/eurostream/producers.py:20 | extracted
obj-04 | queue | topic erasure_requests |  | ingest | [5 empty] | obj-34 | obj-34, obj-37 | [8 empty] | customer_id | ✓ |  | M | manual |  | src/eurostream/producers.py:22 | extracted
obj-05 | queue | topic fraud_alerts |  | ingest | [5 empty] | obj-32 | obj-31 | [8 empty] | customer_id | ✓ | — | L | manual |  | src/eurostream/streaming.py:203 | extracted
obj-06 | file_store | events.db (SqliteBus messages log) |  | ingest | [5 empty] | obj-31, obj-32 | obj-30 | [8 empty] | email, iban, ip_address | ✓ | — | L | manual |  | src/eurostream/bus/sqlite.py:20 | extracted
obj-07 | table | bronze.orders (DuckDB) |  | bronze | [5 empty] | obj-32, obj-37 | obj-32 | [8 empty] | email, iban | ✓ | ✓ | M | manual |  | src/eurostream/warehouse.py:32 | extracted
obj-08 | table | bronze.payments (DuckDB) |  | bronze | [5 empty] | obj-32 | obj-32 | [8 empty] | iban | ✓ | ✓ | L | manual |  | src/eurostream/warehouse.py:41 | extracted
obj-09 | table | bronze.clicks (DuckDB) |  | bronze | [6 empty] | obj-32 | [8 empty] | ip_address | ✓ | ✓ | L | manual |  | src/eurostream/warehouse.py:37 | extracted
obj-10 | table | bronze.fraud_alerts (DuckDB) |  | bronze | [5 empty] | obj-32, obj-37 | obj-32 | [8 empty] | customer_id | ✓ | ✓ | L | manual |  | src/eurostream/warehouse.py:46 | extracted
obj-11 | table | silver.customers (DuckDB) |  | silver | [5 empty] | obj-32, obj-33 | obj-32 | [8 empty] | customer_id, email_hash, iban_hash | ✓ | ✓ | H | manual |  | src/eurostream/warehouse.py:53 | extracted
obj-12 | table | silver.orders / silver.payments (DuckDB) |  | silver | [5 empty] | obj-32 | obj-32 | [8 empty] | customer_id, email_hash, iban_hash | ✓ | ✓ | M | manual |  | src/eurostream/warehouse.py:59 | extracted
obj-13 | table | gold.customer_360 (DuckDB) |  | gold | [5 empty] | obj-37, obj-38, obj-36 | obj-32 | [8 empty] | customer_id, email_hash | ✓ | ✓ | M | manual |  | src/eurostream/warehouse.py:70 | extracted
obj-14 | table | gold.order_facts / gold.fraud_summary (DuckDB) |  | gold | [5 empty] | obj-37, obj-36 | obj-32 | [8 empty] | customer_id | ✓ | ✓ | M | manual |  | src/eurostream/warehouse.py:76 | extracted
obj-15 | table | governance.suppression_registry (DuckDB) |  | governance | [5 empty] | obj-34, obj-37 | obj-34 | [8 empty] | customer_id | ✓ |  | L | manual |  | src/eurostream/warehouse.py:97 | extracted
obj-16 | table | governance.erasure_audit_log (DuckDB) + audit JSONL |  | governance | [5 empty] | obj-37 | obj-34 | [8 empty] | customer_id | ✓ | — | L | manual |  | src/eurostream/governance/erasure.py:253 | extracted
obj-17 | table | governance.watermarks / data_quality_runs / lineage_events / pii_manifest (DuckDB) |  | governance | [5 empty] | obj-32, obj-37 | obj-32, obj-33 | [9 empty] | — |  | L | manual |  | src/eurostream/warehouse.py:94 | extracted
obj-18 | cache | FraudScorer in-memory state (windows, amount history) |  | serving | [5 empty] | obj-31 | obj-31 | [8 empty] | customer_id | ✓ | — | M | manual |  | src/eurostream/streaming.py:91 | extracted
obj-19 | export | data/lake Parquet export (6 files) |  | gold | [5 empty] | obj-36 | obj-32 | [8 empty] | customer_id, email_hash, iban_hash | ✓ | ✓ | L | manual |  | src/eurostream/warehouse.py:795 | extracted
obj-20 | object_store | Hugging Face dataset swadhinbiswas/eustream (public) |  | serving | [5 empty] | obj-37, external | obj-36 | [8 empty] | customer_id, email_hash, iban_hash | ✓ | — | L | manual |  | .github/workflows/orchestrate.yml:90 | extracted
obj-21 | table | Turso libSQL remote mirror |  | serving | [5 empty] | obj-37 | obj-35, obj-34 | [8 empty] | email, iban, ip_address | ✓ |  | M | manual |  | src/eurostream/governance/erasure.py:230 | extracted
obj-22 | file_store | GitHub Actions cache (eurocart.duckdb, events.db) |  | ops | [5 empty] | obj-32 | obj-32 | [9 empty] | ✓ | — | L | manual |  | .github/workflows/orchestrate.yml:22 | extracted
obj-30 | job | Synthetic event producers (eurostream produce) |  | ingest |  |  | on demand / every 4 h via orchestrate.yml | [13 empty] | ✓ |  | L | manual |  | src/eurostream/producers.py:114 | extracted
obj-31 | job | Fraud stream processor (eurostream stream) |  | ingest |  |  | continuous / on demand |  |  |  |  | obj-02 | obj-05 | [7 empty] | ✓ |  | H | manual |  | src/eurostream/streaming.py:54 | extracted
obj-32 | job | Medallion DAG (eurostream transform) |  | transform |  |  | cron 0 */4 * * * (UTC) + every push to master | [13 empty] | ✓ |  | H | manual |  | .github/workflows/orchestrate.yml:4 | extracted
obj-33 | job | Quality gates + PII gate |  | transform |  |  | inside obj-32 | [13 empty] | — |  | M | manual |  | src/eurostream/quality.py:103 | extracted
obj-34 | job | Erasure service (Art. 17 cascade) |  | governance |  |  | on request (sync) — no queued worker started | [13 empty] | ✓ |  | H | manual |  | src/eurostream/governance/erasure.py:108 | extracted
obj-35 | job | Turso sync (eurostream sync-turso) |  | serving |  |  | inside orchestrate.yml | [13 empty] | ✓ |  | M | manual |  | .github/workflows/orchestrate.yml:77 | extracted
obj-36 | job | Hugging Face lake upload |  | serving |  |  | every 4 h (orchestrate.yml) | [13 empty] | ✓ |  | L | manual |  | .github/workflows/orchestrate.yml:85 | extracted
obj-37 | api_endpoint | FastAPI service (≈30 routes incl. /erase, /verify-erasure, /gold/customer-360) |  | serving | [7 empty] | obj-07, obj-10, obj-13, obj-14, obj-15, obj-16, obj-20, obj-21 |  | obj-38, Render web service | [6 empty] | ✓ |  | M | manual |  | src/eurostream/api.py:206 | extracted
obj-38 | ui_view | HTML dashboard (Overview, Fraud, Medallion & 360, GDPR, Prometheus tabs) |  | serving | [7 empty] | obj-37 | [8 empty] | ✓ |  | L | manual |  | src/eurostream/api.py:62 | extracted
obj-39 | job | Schema contract check (eurostream contracts) |  | ops |  |  | CI | [13 empty] | — |  | L | manual |  | src/eurostream/contracts.py:134 | extracted
obj-50 | table | eurostream.bronze — 6 streaming tables (orders, orders_files, payments, clicks, erasure_requests, ingest_quarantine) + fraud_alerts | thuyhoang@kms-technology.com | bronze | 1500 | [11 empty] | 2026-09-28 |  |  | email, iban, ip_address | ✓ | ✓ |  |  |  | SELECT … FROM system.information_schema.tables WHERE table_catalog='eurostream' → bronze.orders:STREAMING_TABLE … | extracted
obj-51 | view | eurostream.silver — materialized views customers, orders, payments, orders_quarantine, payments_quarantine | thuyhoang@kms-technology.com | silver | 1038 | [11 empty] | 2026-09-28 |  |  | email, iban (clear in *_quarantine) | ✓ | ✓ |  |  |  | SELECT … information_schema.columns → silver.orders_quarantine.email:STRING, silver.orders_quarantine.iban:STRING | extracted
obj-52 | view | eurostream.gold — materialized views customer_360, order_facts, fraud_summary | thuyhoang@kms-technology.com | gold | 1038 | [11 empty] | 2026-09-28 |  |  |  | ✓ | ✓ |  |  |  | SELECT count(*) FROM eurostream.gold.customer_360 → 1038 | extracted
obj-53 | table | eurostream.governance — erasure_audit_log, erasure_command_state, pii_manifest, quality_results, suppression_registry | thuyhoang@kms-technology.com | governance | [16 empty] | ✓ |  |  |  |  | DESCRIBE HISTORY eurostream.governance.suppression_registry → 7 MERGE, last 2026-09-28 09:51 | extracted
obj-54 | object_store | UC volumes lake.exports, bronze.inbox, bronze._checkpoints | thuyhoang@kms-technology.com | ops | [21 empty] | SELECT … information_schema.volumes WHERE volume_catalog='eurostream' → lake.exports ¦ bronze.inbox ¦ bronze._checkpoints | extracted
obj-55 | job | Databricks jobs eurostream_pipeline, eurostream_art17_erasure, eurostream_export_lake, eurostream_bootstrap | thuyhoang@kms-technology.com | ops |  |  | unpaused; 27 runs 2026-09-28, none since | 7.9 | user 78641331585392 (a person, not a service principal) | [11 empty] | ✓ |  |  |  |  | system.lakeflow.job_run_timeline → eurostream_pipeline 5 runs / 1 succeeded; export_lake 10/7; art17_erasure 8/7; bootstrap 4/1 | extracted

## Open Questions
Who to ask | ID | Question | Why it matters | Default if unanswered | Impact if wrong | Blocks | Evidence | Email draft
DPO (name: ?) | OQ-03 | Is there any legal basis for processing EU customer data in us-east-2, and in which EU region must the target workspace and metastore live? Where are Aiven Kafka and Turso hosted? | ADR 0001 forbids processing outside the EU; the workspace bills to US_EAST_OHIO. | No basis; target workspace in eu-central-1 | high | SEC-01, FND-01 | docs/adr/0001-eu-region-choice.md:22 | Hi DPO (name: ?), While reviewing docs/adr/0001-eu-region-choice.md:22 we found: ADR 0001 forbids processing outside the EU; the workspace bills to US_EAST_OHIO. Question: Is there any legal basis for processing EU customer data in us-east-2, and in which EU region must the target workspace and metastore live? Where are Aiven Kafka and Turso hosted? If we hear nothing by <date>, we will assume: No basis; target workspace in eu-central-1 Thanks
DPO (name: ?) | OQ-06 | What are the legal erasure deadline and the retention periods per layer? Is 0-hour Delta retention (seen on bronze.fraud_alerts) the intended policy? | Delta time travel and VACUUM must be set against the erasure SLA; 60 s is an app target only. | Erasure within 30 days; 7-day time travel; REORG PURGE + VACUUM after erasure | medium | SEC-03, FND-20 | docs/gdpr_erasure_flow.md §SLA | Hi DPO (name: ?), While reviewing docs/gdpr_erasure_flow.md §SLA we found: Delta time travel and VACUUM must be set against the erasure SLA; 60 s is an app target only. Question: What are the legal erasure deadline and the retention periods per layer? Is 0-hour Delta retention (seen on bronze.fraud_alerts) the intended policy? If we hear nothing by <date>, we will assume: Erasure within 30 days; 7-day time travel; REORG PURGE + VACUUM after erasure Thanks
DPO (name: ?) | OQ-11 | Has any erasure been undone by a full Silver rebuild in production? | The code path exists (FND-02); a regulator-facing question if it happened. | Unknown; check audit log against silver.customers | high | BR-10 | src/eurostream/warehouse.py:484 | Hi DPO (name: ?), While reviewing src/eurostream/warehouse.py:484 we found: The code path exists (FND-02); a regulator-facing question if it happened. Question: Has any erasure been undone by a full Silver rebuild in production? If we hear nothing by <date>, we will assume: Unknown; check audit log against silver.customers Thanks
DPO (name: ?) and Platform owner | OQ-05 | Must the public Hugging Face dataset swadhinbiswas/eustream continue to exist? It holds pseudonymized customer rows, is public by default, and erasure never reaches it. | It is personal data published outside the EU (FND-04). | Retire it; offer an anonymized aggregate via Delta Sharing if needed | high | obj-20, obj-36 | .github/workflows/orchestrate.yml:90 | Hi DPO (name: ?) and Platform owner, While reviewing .github/workflows/orchestrate.yml:90 we found: It is personal data published outside the EU (FND-04). Question: Must the public Hugging Face dataset swadhinbiswas/eustream continue to exist? It holds pseudonymized customer rows, is public by default, and erasure never reaches it. If we hear nothing by <date>, we will assume: Retire it; offer an anonymized aggregate via Delta Sharing if needed Thanks
Fraud/risk owner (name: ?) | OQ-09 | Who owns the fraud thresholds (5 payments / 300 s, 3.0σ) and their production values? | They live only in environment configuration. | Keep defaults | low | BR-04 | src/eurostream/config.py:87 | Hi Fraud/risk owner (name: ?), While reviewing src/eurostream/config.py:87 we found: They live only in environment configuration. Question: Who owns the fraud thresholds (5 payments / 300 s, 3.0σ) and their production values? If we hear nothing by <date>, we will assume: Keep defaults Thanks
Fraud/risk owner (name: ?) | OQ-12 | Is the fraud latency target sub-minute (RFC) or one 300-second window (architecture.md)? | It decides between continuous streaming and triggered micro-batches. | ≤ 60 s | medium | NFR-01 | docs/architecture.md §SLOs | Hi Fraud/risk owner (name: ?), While reviewing docs/architecture.md §SLOs we found: It decides between continuous streaming and triggered micro-batches. Question: Is the fraud latency target sub-minute (RFC) or one 300-second window (architecture.md)? If we hear nothing by <date>, we will assume: ≤ 60 s Thanks
Marketing lead (name: ?) and DPO | OQ-07 | Should marketing consent be the latest value per customer, or 'all orders consented' (current bool_and)? Who filters Gold for marketing today? | The rule is in code and README, but a later opt-in can never take effect; the serving filter is outside the repo. | Latest consent per customer | medium | BR-06, DR-01 | src/eurostream/warehouse.py:496 | Hi Marketing lead (name: ?) and DPO, While reviewing src/eurostream/warehouse.py:496 we found: The rule is in code and README, but a later opt-in can never take effect; the serving filter is outside the repo. Question: Should marketing consent be the latest value per customer, or 'all orders consented' (current bool_and)? Who filters Gold for marketing today? If we hear nothing by <date>, we will assume: Latest consent per customer Thanks
Platform owner (name: ?) | OQ-04 | Which real systems produce orders, clicks and payments, in what format, at what rate and volume? Today all events come from a synthetic generator. | Ingestion pattern (Kafka, Lakeflow Connect, files), sizing and cost depend on it. | Kafka topics as today, ≤ 1M events/day | high | obj-30, INT-01 | src/eurostream/producers.py:114 | Hi Platform owner (name: ?), While reviewing src/eurostream/producers.py:114 we found: Ingestion pattern (Kafka, Lakeflow Connect, files), sizing and cost depend on it. Question: Which real systems produce orders, clicks and payments, in what format, at what rate and volume? Today all events come from a synthetic generator. If we hear nothing by <date>, we will assume: Kafka topics as today, ≤ 1M events/day Thanks
Platform owner (name: ?) | OQ-08 | What salt is used in production (EUROSTREAM_PII_SALT), and may the hashes be re-keyed during migration? | The default salt is public in the repo; a key change re-hashes every Silver/Gold identifier. | Assume compromised; re-key with an HMAC key in a secret scope | medium | DR-02 | src/eurostream/config.py:22 | Hi Platform owner (name: ?), While reviewing src/eurostream/config.py:22 we found: The default salt is public in the repo; a key change re-hashes every Silver/Gold identifier. Question: What salt is used in production (EUROSTREAM_PII_SALT), and may the hashes be re-keyed during migration? If we hear nothing by <date>, we will assume: Assume compromised; re-key with an HMAC key in a secret scope Thanks
Platform owner (name: ?) | OQ-10 | How late can events arrive, and must late events be included in Silver/Gold? | Today they are dropped by the watermark. | Include late events up to 24 h | medium | BR-08 | src/eurostream/warehouse.py:636 | Hi Platform owner (name: ?), While reviewing src/eurostream/warehouse.py:636 we found: Today they are dropped by the watermark. Question: How late can events arrive, and must late events be included in Silver/Gold? If we hear nothing by <date>, we will assume: Include late events up to 24 h Thanks
Platform owner (name: ?) | OQ-13 | What is the Kafka topic retention in Aiven, and may PII be removed from event payloads at the producer? | Erasure never reaches the bus (FND-03). | 7-day retention; tokenize at producer | medium | obj-01, obj-02, obj-03 | src/eurostream/producers.py:114 | Hi Platform owner (name: ?), While reviewing src/eurostream/producers.py:114 we found: Erasure never reaches the bus (FND-03). Question: What is the Kafka topic retention in Aiven, and may PII be removed from event payloads at the producer? If we hear nothing by <date>, we will assume: 7-day retention; tokenize at producer Thanks
Platform owner (name: ?) | OQ-14 | Who uses the public Render API and dashboard, and must they keep working during migration? | Unauthenticated consumers must be re-pointed or cut off. | Demo users only; replace with a Databricks App | medium | obj-37, obj-38 | src/eurostream/api.py:206 | Hi Platform owner (name: ?), While reviewing src/eurostream/api.py:206 we found: Unauthenticated consumers must be re-pointed or cut off. Question: Who uses the public Render API and dashboard, and must they keep working during migration? If we hear nothing by <date>, we will assume: Demo users only; replace with a Databricks App Thanks
Platform owner (name: ?) | OQ-15 | Does anything read Turso besides the API? Can it be retired? | It is a clear-PII mirror (FND-25). | Retire | low | obj-21, obj-35 | src/eurostream/governance/erasure.py:230 | Hi Platform owner (name: ?), While reviewing src/eurostream/governance/erasure.py:230 we found: It is a clear-PII mirror (FND-25). Question: Does anything read Turso besides the API? Can it be retired? If we hear nothing by <date>, we will assume: Retire Thanks
Platform owner (name: ?) with thuyhoang@kms-technology.com (deployer) | OQ-02 | The workspace already runs a eurostream catalog, 4 jobs and Lakeflow pipelines from a databricks/ folder removed from the repo on 2026-10-08. Keep and repair it as the starting point, rebuild from scratch, or discard? | It decides whether wave 1 is a repair or a new build. The deployment is in us-east-2 (FND-01), mostly failing (FND-19) and not in VCS (FND-18). | Treat as a reference design only; rebuild under a bundle in an EU workspace | high | obj-50, obj-51, obj-52, obj-55 | system.lakeflow.job_run_timeline → eurostream_pipeline runs=5 ok=1 | Hi Platform owner (name: ?) with thuyhoang@kms-technology.com (deployer), While reviewing system.lakeflow.job_run_timeline → eurostream_pipeline runs=5 ok=1 we found: It decides whether wave 1 is a repair or a new build. The deployment is in us-east-2 (FND-01), mostly failing (FND-19) and not in VCS (FND-18). Question: The workspace already runs a eurostream catalog, 4 jobs and Lakeflow pipelines from a databricks/ folder removed from the repo on 2026-10-08. Keep and repair it as the starting point, rebuild from scratch, or discard? If we hear nothing by <date>, we will assume: Treat as a reference design only; rebuild under a bundle in an EU workspace Thanks
Platform owner / sponsor (name: ?) | OQ-01 | Why move to Databricks now, and who decides? The RFC calls EuroStream a portfolio artefact; is this assessment for a production go/no-go, a reference migration, or a demo? | The decision the report serves (Axis C) and the depth of scope depend on it. | Treat as a production migration decision for the platform owner | high | SCOPE-01 | docs/rfc/0001-platform-design.md §Problem statement | Hi Platform owner / sponsor (name: ?), While reviewing docs/rfc/0001-platform-design.md §Problem statement we found: The decision the report serves (Axis C) and the depth of scope depend on it. Question: Why move to Databricks now, and who decides? The RFC calls EuroStream a portfolio artefact; is this assessment for a production go/no-go, a reference migration, or a demo? If we hear nothing by <date>, we will assume: Treat as a production migration decision for the platform owner Thanks

## Traceability
Requirement | Title | Rules | Source objects | Target object | Open questions | Review status
FR-01 | Rule-based payment fraud scoring | BR-01, BR-02, BR-03, BR-04 | FraudScorer.score, Settings.fraud_* | <catalog>.bronze.fraud_alerts |  | extracted
NFR-01 | Fraud alert latency |  |  |  | OQ-12 | extracted
SEC-01 | EU data residency for all storage and processing |  |  |  | OQ-03 | extracted
SEC-02 | Right to erasure cascade (Art. 17) | BR-09, BR-10, BR-17 | ErasureService._anonymize_warehouse, ErasureService.is_suppressed, Warehouse.build_silver |  | OQ-06 | extracted
SEC-03 | Erasure SLA 60 seconds (application target) |  |  |  | OQ-06 | extracted
SEC-04 | Auditable erasure trail | BR-16 | ErasureService.execute | <catalog>.governance.erasure_audit_log |  | extracted
DR-01 | Marketing consent propagates to Gold | BR-06, BR-12, BR-18 | QualityGate._check_consent_gated, Settings.consent_default, Warehouse.build_silver | <catalog>.gold.customer_360 | OQ-07 | extracted
DR-02 | Pseudonymize PII at the Silver boundary | BR-05 | Warehouse.build_silver |  | OQ-08 | extracted
DR-03 | Clear PII only in internal Bronze; Bronze never exported |  |  |  |  | extracted
DR-04 | Event schema contracts enforced in CI |  |  |  |  | extracted
DR-05 | Quality gates abort the DAG | BR-11, BR-12 | QualityGate._check_consent_gated, cli.transform DAG |  |  | extracted
DR-06 | Fail on unregistered PII columns | BR-13 | pii.classify_column |  |  | extracted
INT-01 | Event bus Kafka (Aiven) / SQLite local |  |  |  | OQ-04 | extracted
INT-02 | Public Parquet lake on Hugging Face |  |  |  | OQ-05 | extracted
SCOPE-01 | Portfolio artefact, not production |  |  |  | OQ-01 | extracted

## Dependencies
From | To | Kind | Evidence
Synthetic event producers (eurostream produce) (obj-30) | topic orders (obj-01) | writes | src/eurostream/producers.py:114
Synthetic event producers (eurostream produce) (obj-30) | topic payments (obj-02) | writes | src/eurostream/producers.py:21
Synthetic event producers (eurostream produce) (obj-30) | topic clicks (obj-03) | writes | src/eurostream/producers.py:20
Synthetic event producers (eurostream produce) (obj-30) | events.db (SqliteBus messages log) (obj-06) | writes | src/eurostream/cli.py:56
Fraud stream processor (eurostream stream) (obj-31) | topic payments (obj-02) | reads | src/eurostream/streaming.py:241
Fraud stream processor (eurostream stream) (obj-31) | topic fraud_alerts (obj-05) | writes | src/eurostream/streaming.py:261
Fraud stream processor (eurostream stream) (obj-31) | FraudScorer in-memory state (windows, amount history) (obj-18) | writes | src/eurostream/streaming.py:91
Fraud stream processor (eurostream stream) (obj-31) | governance.suppression_registry (DuckDB) (obj-15) | reads | src/eurostream/cli.py:163
Medallion DAG (eurostream transform) (obj-32) | topic orders (obj-01) | reads | src/eurostream/warehouse.py:403
Medallion DAG (eurostream transform) (obj-32) | bronze.orders (DuckDB) (obj-07) | writes | src/eurostream/warehouse.py:242
Medallion DAG (eurostream transform) (obj-32) | bronze.payments (DuckDB) (obj-08) | writes | src/eurostream/warehouse.py:242
Medallion DAG (eurostream transform) (obj-32) | bronze.clicks (DuckDB) (obj-09) | writes | src/eurostream/warehouse.py:242
Medallion DAG (eurostream transform) (obj-32) | bronze.fraud_alerts (DuckDB) (obj-10) | writes | src/eurostream/warehouse.py:815
bronze.orders (DuckDB) (obj-07) | silver.customers (DuckDB) (obj-11) | depends_on | src/eurostream/warehouse.py:484
bronze.orders (DuckDB) (obj-07) | silver.orders / silver.payments (DuckDB) (obj-12) | depends_on | src/eurostream/warehouse.py:508
bronze.payments (DuckDB) (obj-08) | silver.orders / silver.payments (DuckDB) (obj-12) | depends_on | src/eurostream/warehouse.py:521
silver.customers (DuckDB) (obj-11) | gold.customer_360 (DuckDB) (obj-13) | depends_on | src/eurostream/warehouse.py:554
silver.orders / silver.payments (DuckDB) (obj-12) | gold.order_facts / gold.fraud_summary (DuckDB) (obj-14) | depends_on | src/eurostream/warehouse.py:541
bronze.fraud_alerts (DuckDB) (obj-10) | gold.order_facts / gold.fraud_summary (DuckDB) (obj-14) | depends_on | src/eurostream/warehouse.py:575
Quality gates + PII gate (obj-33) | gold.customer_360 (DuckDB) (obj-13) | reads | src/eurostream/quality.py:109
Medallion DAG (eurostream transform) (obj-32) | data/lake Parquet export (6 files) (obj-19) | writes | src/eurostream/warehouse.py:795
Hugging Face lake upload (obj-36) | Hugging Face dataset swadhinbiswas/eustream (public) (obj-20) | writes | .github/workflows/orchestrate.yml:90
data/lake Parquet export (6 files) (obj-19) | Hugging Face dataset swadhinbiswas/eustream (public) (obj-20) | depends_on | .github/workflows/orchestrate.yml:90
Turso sync (eurostream sync-turso) (obj-35) | Turso libSQL remote mirror (obj-21) | writes | .github/workflows/orchestrate.yml:77
Medallion DAG (eurostream transform) (obj-32) | GitHub Actions cache (eurocart.duckdb, events.db) (obj-22) | writes | .github/workflows/orchestrate.yml:22
Erasure service (Art. 17 cascade) (obj-34) | bronze.orders (DuckDB) (obj-07) | writes | src/eurostream/governance/erasure.py:195
Erasure service (Art. 17 cascade) (obj-34) | silver.customers (DuckDB) (obj-11) | writes | src/eurostream/governance/erasure.py:206
Erasure service (Art. 17 cascade) (obj-34) | gold.customer_360 (DuckDB) (obj-13) | writes | src/eurostream/governance/erasure.py:209
Erasure service (Art. 17 cascade) (obj-34) | governance.suppression_registry (DuckDB) (obj-15) | writes | src/eurostream/governance/erasure.py:117
Erasure service (Art. 17 cascade) (obj-34) | governance.erasure_audit_log (DuckDB) + audit JSONL (obj-16) | writes | src/eurostream/governance/erasure.py:253
Erasure service (Art. 17 cascade) (obj-34) | Turso libSQL remote mirror (obj-21) | writes | src/eurostream/governance/erasure.py:230
Erasure service (Art. 17 cascade) (obj-34) | data/lake Parquet export (6 files) (obj-19) | triggers | src/eurostream/governance/erasure.py:153
FastAPI service (≈30 routes incl. /erase, /verify-erasure, /gold/customer-360) (obj-37) | Erasure service (Art. 17 cascade) (obj-34) | calls | src/eurostream/api.py:209
FastAPI service (≈30 routes incl. /erase, /verify-erasure, /gold/customer-360) (obj-37) | gold.customer_360 (DuckDB) (obj-13) | reads | src/eurostream/api.py:486
FastAPI service (≈30 routes incl. /erase, /verify-erasure, /gold/customer-360) (obj-37) | Hugging Face dataset swadhinbiswas/eustream (public) (obj-20) | reads | src/eurostream/api.py:141
FastAPI service (≈30 routes incl. /erase, /verify-erasure, /gold/customer-360) (obj-37) | bronze.fraud_alerts (DuckDB) (obj-10) | reads | src/eurostream/api.py:506
HTML dashboard (Overview, Fraud, Medallion & 360, GDPR, Prometheus tabs) (obj-38) | FastAPI service (≈30 routes incl. /erase, /verify-erasure, /gold/customer-360) (obj-37) | calls | src/eurostream/api.py:62
Databricks jobs eurostream_pipeline, eurostream_art17_erasure, eurostream_export_lake, eurostream_bootstrap (obj-55) | eurostream.bronze — 6 streaming tables (orders, orders_files, payments, clicks, erasure_requests, ingest_quarantine) + fraud_alerts (obj-50) | writes | system.lakeflow.jobs → eurostream_pipeline#409482910379854
eurostream.bronze — 6 streaming tables (orders, orders_files, payments, clicks, erasure_requests, ingest_quarantine) + fraud_alerts (obj-50) | eurostream.silver — materialized views customers, orders, payments, orders_quarantine, payments_quarantine (obj-51) | depends_on | information_schema.tables → silver.* MATERIALIZED_VIEW created 2026-09-28T05:13
eurostream.silver — materialized views customers, orders, payments, orders_quarantine, payments_quarantine (obj-51) | eurostream.gold — materialized views customer_360, order_facts, fraud_summary (obj-52) | depends_on | information_schema.tables → gold.* MATERIALIZED_VIEW created 2026-09-28T05:15

## Sufficiency
Conclusion needed | Evidence required | In hand | State | If missing
Workloads in scope, with target component | Code inventory + workspace inventory | code ✅ · workspace UC ✅ | ✅ | —
Which workloads to retire | Usage ≥ 90 days incl. month/quarter end | none | ❌ | Insufficient evidence. Needs production usage logs. If skipped, everything is migrated "just in case".
Migration effort | Complexity per workload + trial conversion | manual L/M/H ✅ · no trial; prior attempt exists but is unreviewed | ⚠️ range only | —
Erasure completeness on Databricks | Every PII surface + reach proof | code ✅ · workspace current state ✅ (suppressed customer absent in silver/gold, bronze masked) · Delta history / bus / HF ❌ | ⚠️ | Time travel, Kafka and the HF copy may still hold erased data
EU residency | Region of every store and processor | AWS IaC eu-central-1 ✅ · workspace us-east-2 ✅ · Aiven/Turso/HF/GHA ❌ | ⚠️ (one breach proven) | —
Security posture score | SAT or workspace read | SAT run 1 + live SP read ✅, 75% weighted coverage | ✅ score 2/5 | 11 account-level checks not assessed
Data volume / sizing | Row counts and growth from production | workspace only, ~1.5k rows per table, synthetic | ❌ | Cluster and cost sizing cannot be stated
Cost baseline | Current spend + Databricks usage | system.billing.usage 2026-09-25→10-08 ≈ 51.3 DBU ✅ · current hosting spend ❌ | ⚠️ | No business case
Usage window | Source / start / end | none for the legacy runtime; Databricks system.lakeflow.job_run_timeline 2026-09-28→2026-10-05 (8 days, no month end) | ❌ | Nothing can be called orphan

## Sources
Run | Source id | Path | Sha256 | Bytes
2026-10-08_run-01 | src-code | src/eurostream/__init__.py | e8d002b67a6d6d905b3cd1605b8d68bf7063b2200e3be8d8722b97ef0e2ddf28 | 141
2026-10-08_run-01 | src-code | src/eurostream/api.py | 69267005c81569c16a4208893af311a99639195630b9132cbeb10b8c672360c9 | 25738
2026-10-08_run-01 | src-code | src/eurostream/bus/__init__.py | 27c840fe88135f455123dfcb3924bac9248d4f55594d69f0a1e3c87ff1a1f89d | 1140
2026-10-08_run-01 | src-code | src/eurostream/bus/kafka.py | 1503e9a9d5ba2c588532538667939f9dd0850a4b55d1052f1750ec9c0f53c3ba | 8838
2026-10-08_run-01 | src-code | src/eurostream/bus/sqlite.py | 9177fc17e623cc1d8dfbd0594ad6a1c653ab96ff71357565272072c6e6524137 | 7492
2026-10-08_run-01 | src-code | src/eurostream/cli.py | 6099387d8ded1f90b89fa6bfc205ad6202b4f0f3c82a89013c8483c725fe78d1 | 20602
2026-10-08_run-01 | src-code | src/eurostream/config.py | 6b2c39bf96ffabcf757a9a267884e636457d63681f8bbc6094078aa4cd8878f4 | 4585
2026-10-08_run-01 | src-code | src/eurostream/contracts.py | 0a55548a44f76c137c4054df6ae81ba44a8955c54ea5134ae2e55bbb7da6c654 | 5964
2026-10-08_run-01 | src-code | src/eurostream/dashboard.py | da6039507e7a626549b57dd92e8125a9064bafa53d34a5ccc9fb4f3f19d3a0ef | 43581
2026-10-08_run-01 | src-code | src/eurostream/governance/__init__.py | d61d95a0963713a7735de1c4f6ce4621874f48fd96d7d52b53dc34a467e38964 | 263
2026-10-08_run-01 | src-code | src/eurostream/governance/erasure.py | ea77b3a2abb329abb338217bda6bf0e184a3021dc88f66598fef7c702325d4e5 | 11384
2026-10-08_run-01 | src-code | src/eurostream/governance/pii.py | 0ab505fa0b4aeab95fdba9fab4faeb339d8aaa41f1957b90882194a8a01a416e | 6218
2026-10-08_run-01 | src-code | src/eurostream/lineage.py | 0ca784f02b37795be46060dacb14637c7b0157c1bd0a352c8abf67d3d3df72ae | 1975
2026-10-08_run-01 | src-code | src/eurostream/metrics.py | 6d09b03818be71ed7ea81ce8197be4f13b1fe398c78a17718ea47ef817265e9b | 3104
2026-10-08_run-01 | src-code | src/eurostream/models.py | b9f7bf047f101b643c03f89e79ca2a97b465622d00f15a30fe3cce03120f6b8e | 2308
2026-10-08_run-01 | src-code | src/eurostream/orchestration.py | 480e5a63c45fea595eaddc78b96223c50b33d4a6893760251fa95edeea6cfbc4 | 2964
2026-10-08_run-01 | src-code | src/eurostream/portal.py | 91b0aa6a4476f1000605fb39838ed9b1757f95c10049027e23a6f3f19a1fa687 | 2439
2026-10-08_run-01 | src-code | src/eurostream/producers.py | 17c107ed5e3a63ffe0ed37730b5bfcfcdc6fbf04e970e1e0ad0a2d29ce8914fd | 5167
2026-10-08_run-01 | src-code | src/eurostream/quality.py | d7b4b7881f4628621b1a9c517ba25cae5da19dc6dc84d1f49d0cdd832c8e78cd | 4816
2026-10-08_run-01 | src-code | src/eurostream/streaming.py | f1b9a2fb700f67aa950de5d52d4f1348de8827bb76ffb2ac1e44a17ccbcef470 | 10199
2026-10-08_run-01 | src-code | src/eurostream/turso.py | 887d22f8dc6adf940874477241dc392633ad54edf12d1c2e24b6a9c99c853dd6 | 13151
2026-10-08_run-01 | src-code | src/eurostream/types.py | e59e791a4d4af34557c5231e3a5b7aaed88e58fee2be7df789023e33e28d9a1c | 103
2026-10-08_run-01 | src-code | src/eurostream/warehouse.py | 69d02dffe618f4560e2a64b04cb1ac5ea541a61c09e5a7cb8acc3a34d289ba0b | 37413
2026-10-08_run-01 | src-code | governance/contracts.json | 9ec855c5a18ae17967b702953705f32bd3257c85adef16223513f465ce0be9dd | 4386
2026-10-08_run-01 | src-code | governance/pii_manifest.json | fba0a94f12697c89f093884e31eb10ff79680b0f3e35fae1990778010681635c | 98
2026-10-08_run-01 | src-code | tests/databricks/test_bundle_contracts.py | 9c6fc9321ef02c6b144d29d6527f87809ffa5ac2625e2971c4c88534d15c3e24 | 3393
2026-10-08_run-01 | src-code | tests/databricks/test_critical_repairs.py | c43c513f04cdba013dd08cea4ebd7338dab6940c375560c8adc899afcff90db2 | 7143
2026-10-08_run-01 | src-code | tests/databricks/test_notebook_contracts.py | 406d1a909e2266cb38325e7342721ab93e797529d281098de5627834efddba82 | 9409
2026-10-08_run-01 | src-ci | .github/workflows/ci.yml | 307367d112e4872034ed4b646a1781f92cb530c6d6f14de70b458d58acfc1b90 | 2031
2026-10-08_run-01 | src-ci | .github/workflows/deploy-space.yml | bc1682f1273f8986ccb3e807161095a142a95419accf441b8f6292558328d17b | 2870
2026-10-08_run-01 | src-ci | .github/workflows/orchestrate.yml | 76fc618dd38d0af180f25a16400396c13117bf0c5bd80cf786995823d7d3f8b7 | 4348
2026-10-08_run-01 | src-iac | infra/main.tf | dd61e6373877c22380d30252ee6f2b92947247317e7d7f3d46485a299b285514 | 4029
2026-10-08_run-01 | src-iac | render.yaml | db2f31a25f14dbbc3c216d7421c7536087b2580ec716c2aa10ae8621c4f20763 | 911
2026-10-08_run-01 | src-iac | Dockerfile | c499c8b8f3d1aab50bb5d5acec2084e3b759d22d43d3af16049009e0fd96d890 | 1467
2026-10-08_run-01 | src-iac | docker-compose.yml | ffb3ade6d3783e45a0332a4f68fe02fade51a6a8375a565c27b2addad134f389 | 1058
2026-10-08_run-01 | src-iac | .env.example | 8924f052985f2f9e296f79882d7bb4778ef4beea7a9c097f0c72abe2e2d62057 | 1299
2026-10-08_run-01 | src-docs | README.md | fdb2a70c840fca08b997944fe8a188d2f602852094e83592fb63a9f1a1b35038 | 21786
2026-10-08_run-01 | src-docs | docs/adr/0001-eu-region-choice.md | 781913b1f9cf2b0a3e731c9ea5a6ee97eaf39a04248c544106a061a2b8df4418 | 2287
2026-10-08_run-01 | src-docs | docs/adr/0002-event-bus.md | 32f366c5308a44f0600a77effba0c40da404ced2827fedcf15f19faaaf9e6193 | 2667
2026-10-08_run-01 | src-docs | docs/adr/0003-pii-classification.md | ad415baeb30c533763ca3af1023996f5ec2eb7070ceb355219d61033e379dc0f | 3323
2026-10-08_run-01 | src-docs | docs/architecture.md | 788a0cfe42a5bf5d7eaef79f594a921cf8629259642a9187d901382c091527e4 | 9375
2026-10-08_run-01 | src-docs | docs/gdpr_erasure_flow.md | 4b40f9fe04c091b6f9006486b1899f8011b0467b06f3933c766ffe2c6443abff | 6808
2026-10-08_run-01 | src-docs | docs/postmortem/inc-2026-001-pii-false-positive.md | 3a187c6b495ea4b64850d6fb020c126fbd9e967436dbe6450102ac5eb67c4311 | 3508
2026-10-08_run-01 | src-docs | docs/rfc/0001-platform-design.md | 02dd6385cac330bdd35b868990067c51130fd91380be2c79142ada4fce3c9252 | 11828
2026-10-08_run-01 | src-docs | paper/paper.md | 16ca83431c729d3da1cf2f91d0c49764bb104d3cb295f30f8f670fa44f670b8e | 11254