## Summary
Project | eurostream
Decision (Axis C) | > This report is for **the delivery lead / repo owner** to decide **whether the Databricks build is ready to become the primary EuroStream runtime, and which Python / DuckDB / Turso components to migrate, keep or retire**, before **no fixed date**. `stated` (decision) · `assumed` (audience, date) — OQ-04
Counts
Requirements | 0
Business rules | 0
Inventory objects | 9
Findings | 12
Readiness (lowest scored of 5) | 1
Open questions (open) | 9
of which blocking (impact high) | 4
Rationalization
migrate | 5
modernize | 3
retire | 0
defer | 1
undecided | 0
rule_status
Evidence gaps (❌/⚠️) | 5
Go / no-go on cut-over — Feature parity (code), deployed objects (UC), working runs (job history), security score
Per-component disposition (migrate / keep / retire) — Python inventory + Databricks counterpart + consumers
Erasure (Art. 17) parity — Both erasure paths read; a rehearsal run on Databricks
Cost baseline — `system.billing.usage` ≥ 30 days of steady running
**Usage window** — `system.lakeflow.job_run_timeline` 90d

## Readiness
dimension | score | counted | basis | rationale | needs | evidence | status
data | 3 | TRUE | workspace | Target Bronze/Silver/Gold/governance objects exist (37) and match the design, but nothing has been written to them since 2026-09-28 and Silver hash continuity is open. |  | eurostream.information_schema.tables grouped by schema/type | reviewed
logic | 4 | TRUE | code | Fraud thresholds and the four quality gates match across stacks; one alert rule differs (GEO_MISMATCH); Databricks erasure reaches more stores than Python. |  | databricks/notebooks/03_fraud_streaming.py:378-388 | reviewed
governance | 1 | TRUE | workspace | PII masks, tags and row filters from 50_grants_and_tags.sql are absent in the deployed catalog, and the workspace runs in US East (Ohio) against the EU-only ADR. |  | eurostream.information_schema.column_masks → 0 rows; system.billing.usage 90d → sku_name LIKE '%US_EAST_OHIO' | reviewed
security | 2 | TRUE | sat | Read from the client's own SAT run 1 (2026-10-05) by thuyhoang@kms-technology.com via read-only SQL: 23 of 52 checks failed; severity-weighted pass share 59% (61/103); 3 failed High checks cap the score at 2 (security-posture scoring rule, applied by hand — posture.py could not run here). | not assessed — live workspace read (posture.py run --workspace) to cross-check SAT; GOV-21 and GOV-34 are known SAT false-fail candidates — if both are rejected on review the cap lifts to 3 | sat.security_analysis.security_checks run_id=1 ⨝ security_best_practices, score=1 | reviewed
operations | 1 | TRUE | workspace | All Databricks runs fall on one day (2026-09-28) with failures in every job; fraud stream, quality gate and orchestrator are not deployed; the bundle ships schedules paused and the UI is the declared source of truth. |  | system.lakeflow.jobs ⨝ job_run_timeline, 90d, name LIKE '%eurostream%' | reviewed

## Decisions
id | question | why | ask | default | impact_if_wrong | blocking | evidence
OQ-01 | Why cut over now? If both runtimes keep running side by side for 12 more months, what breaks? | Sets how aggressively to retire Python components and whether parity must be exact. | Repo owner (name: ?) | Driver = run one supported platform; retire what Databricks covers | high |  | databricks/README.md:7
OQ-02 | Where does the Python stack run today (Render, Docker, GitHub Actions orchestrate.yml, Turso), and who uses its API/dashboard? | Retiring it switches off whatever is deployed; unknown consumers block 'retire'. Turso holds PII Databricks erasure never reaches. | Repo owner (name: ?) | Treat Render, GitHub Actions and Turso as live; their disposition stays 'defer' until confirmed | high | FND-07, FND-09 | src/eurostream/governance/erasure.py:215
OQ-06 | Is a US-region (us-east-2) workspace acceptable, or must production move to an EU-region workspace per ADR-0001? | Every billed SKU is US_EAST_OHIO; ADR-0001 requires EU-only processing. | Repo owner / DPO (name: ?) | Production needs an EU workspace; this one is a rehearsal environment | high | FND-02 | system.billing.usage 90d → sku_name LIKE '%US_EAST_OHIO'
OQ-07 | Was 50_grants_and_tags.sql (masks, tags, row filters) never run, or run and later dropped? Who applies it? | 0 masks, 0 routines, 0 tags in the deployed catalog. If my read identity lacks visibility, this could be a false negative. | Workspace admin (name: ?) | Treat as not applied; blocking until applied and re-read | high | FND-01 | eurostream.information_schema.column_masks → 0 rows

## Rationalization
object_id | kind | name | disposition | wave | used | usage_window_days | covers_month_end | complexity | complexity_source | on_critical_path | rule_status_max | owner_agreed | target_component | blocking | evidence | notes
obj-dbx-jobs | job | Deployed jobs: eurostream_bootstrap, eurostream_pipeline, eurostream_export_lake, eurostream_art17_erasure | modernize | 1 | TRUE | 90 | FALSE |  |  | TRUE |  |  | Bundle-deployed jobs from databricks/dab/resources/jobs.yml (replace the UI-created ones) | OQ-03 | system.lakeflow.jobs name LIKE '%eurostream%' → 4 jobs | Target-side clean-up: the bundle becomes the deployment source of truth (FND-04, FND-05).
obj-py-api | api_endpoint | FastAPI app (/erase, /erasure-requests, /produce, /stream, /transform, /quality-gate, /metrics, /sync-turso, gold/governance reads) | modernize | 2 | [5 empty] | FALSE |  |  | Databricks App (OBO reads + preview-token erasure); ingest/transform endpoints become Lakeflow Jobs; erasure SLA metric → SQL alert (to build) | OQ-02 | src/eurostream/api.py:206 | Retire only when OQ-02 confirms no consumer outside the demo. No /metrics equivalent exists in the App yet.
obj-py-bus | queue | Python event bus (SQLite / Kafka adapter): orders, clicks, payments, erasure_requests | migrate | 1 | [5 empty] | TRUE |  |  | Kafka → Lakeflow Bronze streaming tables eurostream.bronze.{orders,clicks,payments,erasure_requests} + ingest_quarantine (already built) |  | databricks/dlt/bronze_ingest.py:609-729 | All four topics already ingested on Databricks; SQLite bus is local-only and needs no counterpart.
obj-py-duckdb | table | DuckDB warehouse bronze/silver/gold/governance | migrate | 1 | [5 empty] | TRUE |  |  | Unity Catalog eurostream.{bronze,silver,gold,governance} (37 objects deployed) | OQ-09 | eurostream.information_schema.tables grouped by schema/type | No history backfill assumed: Silver/Gold are rebuilt from Bronze on Databricks (OQ-09 default).
obj-py-fraud | job | Python FraudStreamProcessor | migrate | 1 | [5 empty] | TRUE | CONFLICT |  | Lakeflow Job eurostream_fraud_continuous running databricks/notebooks/03_fraud_streaming.py (defined in bundle, not deployed) | OQ-08 | databricks/notebooks/03_fraud_streaming.py:378-388 | Velocity and z-score rules match. GEO_MISMATCH differs (FND-06); migrate assumes the OQ-08 default (keep once-per-window), which means a change to the Databricks notebook.
obj-py-lake | export | Parquet lake → Hugging Face swadhinbiswas/eustream | migrate | 2 | [5 empty] | FALSE |  |  | Job eurostream_export_lake → /Volumes/eurostream/lake/exports, sync_huggingface=true | OQ-05 | databricks/notebooks/04_export_lake.py:20 | Export job ran 7 of 10 times successfully on 2026-09-28.
obj-py-quality | job | Python quality gates (uniqueness, PII not clear, consent gating, RI) | migrate | 1 | [5 empty] | TRUE |  |  | Lakeflow Job eurostream_quality_gate running databricks/notebooks/01_quality_gates.py (defined in bundle, not deployed) |  | databricks/notebooks/01_quality_gates.py:49-178 | Same four checks as src/eurostream/quality.py:48-55.
obj-py-schedule | job | GitHub Actions orchestrate.yml (every 4h) | modernize | 2 | [5 empty] | TRUE |  |  | Lakeflow Job eurostream_orchestrator, cron 0 0 */4 * * ? (bundle; unpause after wave 1 exit) | OQ-02 | databricks/dab/resources/jobs.yml:374-376 | Switch off the GitHub Actions schedule only after the Databricks orchestrator has run cleanly.
obj-py-turso | external_consumer | Turso libSQL mirror | defer | [6 empty] | FALSE |  |  |  | OQ-02 | src/eurostream/governance/erasure.py:215 | Likely retire (the Databricks App's own Operations page calls it not a dependency), but no usage evidence or owner agreement yet. If kept, Databricks erasure must reach it.

## Findings
id | severity | category | layer | title | impact | detail | when migrated | evidence kind | requirements_raised | questions_raised | evidence | status
FND-01 | critical | security | store | PII masks, tags and row filters defined in code are not applied in the workspace | Clear-text Bronze PII (email, IBAN, IP) readable by anyone with SELECT; contradicts Art.25/32 design. Blocks cut-over. | 50_grants_and_tags.sql:357-447 creates pii_clear_text_mask and masks bronze email/iban/ip_address. Deployed catalog: 0 column masks, 0 routines, 0 column tags, 0 row filters. | carried | stated |  | OQ-07 | SELECT * FROM eurostream.information_schema.column_masks → 0 rows; routines/column_tags/row_filters → 0 rows; databricks/sql/50_grants_and_tags.sql:425-447 | reviewed
FND-03 | high | ops | ops | Databricks build ran on one day only (2026-09-28); half the jobs failed at least once | No evidence the target runs unattended; go/no-go cannot rest on one rehearsal day. | 4 jobs in system.lakeflow: eurostream_bootstrap 1/4 ok, eurostream_pipeline 1/5 ok, eurostream_export_lake 7/10 ok, eurostream_art17_erasure 7/8 ok. All runs 2026-09-28 04:50-09:59 UTC; none since. | carried | stated |  |  | system.lakeflow.jobs ⨝ job_run_timeline, 90d, name LIKE '%eurostream%' | reviewed
FND-11 | high | security | ops | SAT run 1 (2026-10-05): 23 of 52 checks failed, 3 of them High | Workspace not production-hardened for EU personal data. | High: GOV-21 metastore admin not a group, GOV-34 audit logs not monitored, NS-11 IP access list not enforced. Medium incl. GOV-42 jobs not run as service principal, DP-5/DP-11 result downloads enabled. | carried | stated |  |  | sat.security_analysis.security_checks run_id=1 ⨝ security_best_practices, score=1 | reviewed
FND-06 | medium | logic | transform | GEO_MISMATCH fires once per window in Python, on every event in Databricks | Alert volume changes on cut-over; downstream fraud_summary counts not comparable. | Python sets stats.geo_mismatch and skips repeats in the window (streaming.py:134-146). Databricks yields an alert for every mismatched payment (03_fraud_streaming.py:378-388). Other thresholds (velocity 5/300s, z>3, baseline 3) match. | carried | stated |  | OQ-08 | src/eurostream/streaming.py:134-146; databricks/notebooks/03_fraud_streaming.py:378-388 | reviewed
FND-08 | medium | governance | store | pii_manifest.json omits payments.iban and clicks.ip_address | Manifest-driven tagging or audits under-report PII. | Manifest lists only bronze.orders email/iban. Python erasure anonymizes payments.iban and clicks.ip_address (erasure.py:199-206); Databricks masks them (50_grants_and_tags.sql:437-441). | carried | stated |  |  | governance/pii_manifest.json:1-10 | reviewed
FND-12 | low | governance | serving | Databricks erasure is broader than Python but does not verify the remote Hugging Face copy | Public HF dataset may retain erased customers if de-identification is ever incomplete. | 02_article17_erasure.py covers Bronze masks, quarantine, fraud_alerts purge, Silver/Gold refresh and lake Volume rewrite; its verify scope says remote Hugging Face not verified (:911). Python erasure never touches the lake export. | carried | stated |  | OQ-05 | databricks/notebooks/02_article17_erasure.py:911 | reviewed
FND-04 | high | ops | ops | Deployed jobs do not match the bundle; fraud stream, quality gate and orchestrator are absent | Continuous fraud scoring and the 4-hourly DAG that replace the Python GitHub Actions run do not exist in the target. | Bundle defines 8 jobs (jobs.yml:15-368) incl. eurostream_fraud_continuous, quality_gate, orchestrator. Workspace has 4 UI-created jobs: eurostream_bootstrap, eurostream_pipeline, eurostream_export_lake, eurostream_art17_erasure. | redesign | stated |  | OQ-03 | databricks/dab/resources/jobs.yml:15-44; system.lakeflow.jobs name LIKE '%eurostream%' → 4 jobs | reviewed
FND-02 | high | governance | ops | Workspace runs in US East (Ohio); ADR-0001 requires EU-only processing | EU residency claim does not hold for the Databricks target; a cut-over moves EU personal data to the US. | All billed SKUs are *_US_EAST_OHIO, including INTER_REGION_EGRESS. ADR-0001 says all storage and processing is pinned to EU regions; infra/main.tf pins eu-central-1. | redesign | stated |  | OQ-06 | system.billing.usage 90d → sku_name LIKE '%US_EAST_OHIO'; docs/adr/0001-eu-region-choice.md:22 | reviewed
FND-09 | medium | security | serving | Python API exposes erasure and data endpoints without authentication, CORS * | Risk persists while the Python stack stays live; resolved by the Databricks App (OBO + preview token) if retired. | api.py:51-52 adds CORSMiddleware allow_origins=['*']; POST /erasure-requests (:173) and /erase/{customer_id} (:206) declare no auth dependency. | resolved-by-target | stated |  | OQ-02 | src/eurostream/api.py:206 | reviewed
FND-07 | medium | dependency | store | Turso sync and its erasure cascade have no Databricks counterpart | Turso is either retired at cut-over or left holding PII that Databricks erasure never reaches. | Python dual-writes to Turso (src/eurostream/turso.py) and cascades erasure there (erasure.py:215-240). No Turso reference in databricks/ pipelines, notebooks or SQL. | redesign | stated |  | OQ-02 | src/eurostream/governance/erasure.py:215 | reviewed
FND-10 | medium | security | transform | Hard-coded default PII salt in Python; Databricks reads it from Spark conf | Hashes are reversible by dictionary if the default is used; salts differ between stacks so Silver hashes will not match after cut-over. | config.py:22 PII_SALT = "eurostream-pii-salt" used by hash_pii and build_silver. Databricks silver_pseudonymize.py:31 reads spark.conf eurostream.pii.salt. | resolved-by-target | stated |  | OQ-09 | src/eurostream/config.py:22; databricks/dlt/silver_pseudonymize.py:31 | reviewed
FND-05 | medium | ops | ops | Bundle ships continuous ingest and the 4-hourly orchestrator PAUSED; UI is declared source of truth | Cut-over is not reproducible from the repo; a rebuild depends on an unshared runbook. | jobs.yml:20 and :376 pause_status PAUSED. databricks.yml:3 and README:91 say the manual UI path is the source of truth; runbook docs/databricks/ is gitignored. | redesign | stated |  | OQ-03 | databricks/dab/resources/jobs.yml:376; databricks/dab/databricks.yml:3 | reviewed

## Business Rules
id | name | rule_status | logic | plain | anchor | config_driven | in_spec | requirements | open_questions | locator | status

## Requirements
id | type | priority | title | statement | domain | inferred | confidence | conflicts | open_questions | target_layer | target_object | owner | evidence | status

## Inventory
id | kind | name | owner | layer_guess | row_estimate | size_gb | schedule | avg_runtime_min | run_as | readers | writers | reads | writes | consumers | exec_count_90d | last_read_at | last_write_at | last_exec_at | orphan | pii_candidates | holds_pii | erasure_reaches | complexity | complexity_source | disposition | evidence | status
obj-dbx-jobs | job | Deployed jobs: eurostream_bootstrap, eurostream_pipeline, eurostream_export_lake, eurostream_art17_erasure |  | ops | [12 empty] | 2026-09-28 | [8 empty] | system.lakeflow.jobs name LIKE '%eurostream%' | reviewed
obj-py-api | api_endpoint | FastAPI app (/erase, /erasure-requests, /produce, /stream, /transform, /quality-gate, /metrics, /sync-turso, gold/governance reads) |  | serving | [16 empty] | TRUE |  |  |  |  | src/eurostream/api.py:206 | reviewed
obj-py-bus | queue | Python event bus (SQLite / Kafka adapter): orders, clicks, payments, erasure_requests |  | ingest | [16 empty] | TRUE | FALSE |  |  |  | src/eurostream/producers.py | reviewed
obj-py-duckdb | table | DuckDB warehouse bronze/silver/gold/governance |  | store | [16 empty] | TRUE | TRUE |  |  |  | src/eurostream/warehouse.py | reviewed
obj-py-fraud | job | Python FraudStreamProcessor |  | transform | [16 empty] | FALSE | TRUE |  |  |  | src/eurostream/streaming.py:56 | reviewed
obj-py-lake | export | Parquet lake → Hugging Face swadhinbiswas/eustream |  | serving | [16 empty] | FALSE | FALSE |  |  |  | .github/workflows/orchestrate.yml | reviewed
obj-py-quality | job | Python quality gates (uniqueness, PII not clear, consent gating, RI) |  | ops | [21 empty] | src/eurostream/quality.py:48-55 | reviewed
obj-py-schedule | job | GitHub Actions orchestrate.yml (every 4h) |  | ops | [21 empty] | .github/workflows/orchestrate.yml | reviewed
obj-py-turso | external_consumer | Turso libSQL mirror |  | store | [16 empty] | TRUE | TRUE |  |  |  | src/eurostream/governance/erasure.py:215 | reviewed

## Open Questions
ask | id | question | why | default | impact_if_wrong | blocking | evidence | email_draft
Fraud rule owner (name: ?) | OQ-08 | Which GEO_MISMATCH behaviour is intended: once per customer per 5-minute window (Python) or every event (Databricks)? | Changes alert volume and fraud_summary counts after cut-over. | Keep Python behaviour (once per window) | medium | FND-06 | src/eurostream/streaming.py:134-146 | Hi Fraud rule owner (name: ?), While reviewing src/eurostream/streaming.py:134-146 we found: Changes alert volume and fraud_summary counts after cut-over. Question: Which GEO_MISMATCH behaviour is intended: once per customer per 5-minute window (Python) or every event (Databricks)? If we hear nothing by <date>, we will assume: Keep Python behaviour (once per window) Thanks
Repo owner (name: ?) | OQ-01 | Why cut over now? If both runtimes keep running side by side for 12 more months, what breaks? | Sets how aggressively to retire Python components and whether parity must be exact. | Driver = run one supported platform; retire what Databricks covers | high |  | databricks/README.md:7 | Hi Repo owner (name: ?), While reviewing databricks/README.md:7 we found: Sets how aggressively to retire Python components and whether parity must be exact. Question: Why cut over now? If both runtimes keep running side by side for 12 more months, what breaks? If we hear nothing by <date>, we will assume: Driver = run one supported platform; retire what Databricks covers Thanks
Repo owner (name: ?) | OQ-02 | Where does the Python stack run today (Render, Docker, GitHub Actions orchestrate.yml, Turso), and who uses its API/dashboard? | Retiring it switches off whatever is deployed; unknown consumers block 'retire'. Turso holds PII Databricks erasure never reaches. | Treat Render, GitHub Actions and Turso as live; their disposition stays 'defer' until confirmed | high | FND-07, FND-09 | src/eurostream/governance/erasure.py:215 | Hi Repo owner (name: ?), While reviewing src/eurostream/governance/erasure.py:215 we found: Retiring it switches off whatever is deployed; unknown consumers block 'retire'. Turso holds PII Databricks erasure never reaches. Question: Where does the Python stack run today (Render, Docker, GitHub Actions orchestrate.yml, Turso), and who uses its API/dashboard? If we hear nothing by <date>, we will assume: Treat Render, GitHub Actions and Turso as live; their disposition stays 'defer' until confirmed Thanks
Repo owner (name: ?) | OQ-03 | Can you share the private runbook docs/databricks/ (gitignored), and should the bundle become the deployment source of truth? | Deployed jobs differ from the bundle; the UI path is declared the source of truth but is not in the repo. | Make the bundle the source of truth before cut-over | medium | FND-04, FND-05 | databricks/dab/databricks.yml:3 | Hi Repo owner (name: ?), While reviewing databricks/dab/databricks.yml:3 we found: Deployed jobs differ from the bundle; the UI path is declared the source of truth but is not in the repo. Question: Can you share the private runbook docs/databricks/ (gitignored), and should the bundle become the deployment source of truth? If we hear nothing by <date>, we will assume: Make the bundle the source of truth before cut-over Thanks
Repo owner (name: ?) | OQ-05 | Does anyone consume the public Parquet lake on Hugging Face, and must Databricks keep publishing it (sync_huggingface is off by default)? | Python publishes it every 4h from GitHub Actions; Databricks writes /Volumes/eurostream/lake/exports and only pushes to HF when the flag is set; erasure does not verify the remote copy. | Keep publishing (public link in README) | medium | FND-12 | databricks/notebooks/04_export_lake.py:20 | Hi Repo owner (name: ?), While reviewing databricks/notebooks/04_export_lake.py:20 we found: Python publishes it every 4h from GitHub Actions; Databricks writes /Volumes/eurostream/lake/exports and only pushes to HF when the flag is set; erasure does not verify the remote copy. Question: Does anyone consume the public Parquet lake on Hugging Face, and must Databricks keep publishing it (sync_huggingface is off by default)? If we hear nothing by <date>, we will assume: Keep publishing (public link in README) Thanks
Repo owner (name: ?) | OQ-09 | Is the production salt the same secret in both stacks, and must Silver hashes stay comparable across the cut-over? | Python defaults to a hard-coded salt; Databricks reads spark conf. Different salts break joins on hashed PII and historical comparison. | Rebuild Silver on Databricks from Bronze; no hash continuity needed | medium | FND-10 | src/eurostream/config.py:22 | Hi Repo owner (name: ?), While reviewing src/eurostream/config.py:22 we found: Python defaults to a hard-coded salt; Databricks reads spark conf. Different salts break joins on hashed PII and historical comparison. Question: Is the production salt the same secret in both stacks, and must Silver hashes stay comparable across the cut-over? If we hear nothing by <date>, we will assume: Rebuild Silver on Databricks from Bronze; no hash continuity needed Thanks
Repo owner / DPO (name: ?) | OQ-06 | Is a US-region (us-east-2) workspace acceptable, or must production move to an EU-region workspace per ADR-0001? | Every billed SKU is US_EAST_OHIO; ADR-0001 requires EU-only processing. | Production needs an EU workspace; this one is a rehearsal environment | high | FND-02 | system.billing.usage 90d → sku_name LIKE '%US_EAST_OHIO' | Hi Repo owner / DPO (name: ?), While reviewing system.billing.usage 90d → sku_name LIKE '%US_EAST_OHIO' we found: Every billed SKU is US_EAST_OHIO; ADR-0001 requires EU-only processing. Question: Is a US-region (us-east-2) workspace acceptable, or must production move to an EU-region workspace per ADR-0001? If we hear nothing by <date>, we will assume: Production needs an EU workspace; this one is a rehearsal environment Thanks
User | OQ-04 | Who reads the report and by when must the cut-over decision be made? | Axis C audience and date are assumed. | Delivery lead; no deadline | low |  | session 2026-10-06 | Hi User, While reviewing session 2026-10-06 we found: Axis C audience and date are assumed. Question: Who reads the report and by when must the cut-over decision be made? If we hear nothing by <date>, we will assume: Delivery lead; no deadline Thanks
Workspace admin (name: ?) | OQ-07 | Was 50_grants_and_tags.sql (masks, tags, row filters) never run, or run and later dropped? Who applies it? | 0 masks, 0 routines, 0 tags in the deployed catalog. If my read identity lacks visibility, this could be a false negative. | Treat as not applied; blocking until applied and re-read | high | FND-01 | eurostream.information_schema.column_masks → 0 rows | Hi Workspace admin (name: ?), While reviewing eurostream.information_schema.column_masks → 0 rows we found: 0 masks, 0 routines, 0 tags in the deployed catalog. If my read identity lacks visibility, this could be a false negative. Question: Was 50_grants_and_tags.sql (masks, tags, row filters) never run, or run and later dropped? Who applies it? If we hear nothing by <date>, we will assume: Treat as not applied; blocking until applied and re-read Thanks

## Traceability
requirement | title | rules | source_objects | target_object | open_questions | status

## Dependencies
from | to | kind | evidence

## Sufficiency
Conclusion needed | Evidence required | In hand | State | If missing
Go / no-go on cut-over | Feature parity (code), deployed objects (UC), working runs (job history), security score | code ✅ · UC ✅ · runs ✅ (one day only, FND-03) · SAT ✅ | ⚠️ | Go/no-go can only be "not yet, conditions X"
Per-component disposition (migrate / keep / retire) | Python inventory + Databricks counterpart + consumers | code ✅ · consumers ❌ (OQ-02, OQ-05) | ⚠️ | "Retire" stays `defer` for Turso, Render API, HF publish
Erasure (Art. 17) parity | Both erasure paths read; a rehearsal run on Databricks | code ✅ · 8 erasure runs on 2026-09-28 (7 ok) | ⚠️ | Rehearsal outputs not inspected
Deployed = code (no drift) | UC objects vs `databricks/sql`, `dlt/`, `dab/` | ✅ | ✅ | Drift found: FND-01, FND-04
Security readiness | SAT run on the target workspace | SAT run 1, 2026-10-05: 23/52 failed | ✅ | —
EU residency | Workspace region | `system.billing.usage` SKUs US_EAST_OHIO | ✅ | Conflict: FND-02
Cost baseline | `system.billing.usage` ≥ 30 days of steady running | 2026-09-25 → 2026-10-06, rehearsal only | ❌ | No run-rate cost statement; only "rehearsal cost"
**Usage window** | `system.lakeflow.job_run_timeline` 90d | 2026-09-28 04:50 → 09:59 UTC (all runs) | ❌ | Nothing on Databricks has steady-state usage

## Sources
run | source_id | path | sha256 | bytes
2026-10-06_run-01 | src-py | src/eurostream/
2026-10-06_run-01 | src-dbx | databricks/
2026-10-06_run-01 | src-gov | governance/pii_manifest.json
2026-10-06_run-01 | src-docs | docs/adr/0001-eu-region-choice.md
2026-10-06_run-02 | registers | discovery/eurostream/registers/*.jsonl
2026-10-06_run-02 | src-dbx | databricks/dab/resources/jobs.yml, databricks/dab/resources/pipelines.yml, databricks/dab/databricks.yml